## Summary
Manday Summary Sheet
Resource Allocation - Phase 1 | Man-day | Man-hour
Project Manager | 30 | 240
System Analyst | 42 | 336
Resource Allocation - Phase 2
Project Manager | 39 | 312
System Analyst | 411 | 3288
Analyst Programmer | 152.5 | 1220
Resource Allocation - Phase 1&2 |  |  | Rate per hours (HKD)
Project Manager | 69 | 552 | 560 | 309120
System Analyst | 453 | 3624 | 560 | 2029440
Analyst Programmer | 152.5 | 1220 | 490 | 597800
|  |  | HKD | 2936360
Note on F9: Edward Leung: Org:

## Timeline and Est (Phase I)
Phase I Schedule
| Nov |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13
High Level Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Migration Planning and Environment Assessment
Site Discovery / Environment Assessment | bar: 2016-11-14 to 2016-11-21
Planning, Identify Business and Technical Req | bar: 2016-11-28 to 2016-12-12
Migration Plan Definition
Development Migration Plan | bar: 2016-12-19 to 2016-12-26
Develop Migration Test Plan and Testing Guidelines | bar: 2017-01-02 to 2017-01-09
Migration Verification Process
Establish POC environment | bar: 2017-01-16
Conduct Migration and Functional Test | bar: 2017-01-23 to 2017-01-30
Production Server Migration and Switch Over
Migration for Production | bar: 2017-02-06
Conduct Migration and Functional Test | bar: 2017-02-13
Resource
Project Manager
Infrastructure Architect
System Analyst
Analyst Programmer
Resource Allocation
Project Manager | 2016-11-14: 30
System Analyst | 2016-11-14: 42

## Timeline and Est (Phase II)
Phase II Schedule
| Nov |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar
| 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13
High Level Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Project Initialization | bar: 2016-11-14
Hardware / VPN Setup | bar: 2016-11-14 to 2016-12-26
Planning, Identify Business and Technical Req | bar: 2016-11-21 to 2016-11-28
System Development | bar: 2016-12-05 to 2017-01-30
System Test | bar: 2017-01-02 to 2017-01-30
User Acceptance Test | bar: 2017-01-23 to 2017-02-13
Operation Acceptance Test | bar: 2017-01-02 to 2017-01-09
Capacity, Performance and Penetration Test | bar: 2017-02-06 to 2017-02-13
Training | bar: 2017-01-23
Implementation | bar: 2017-02-20
Documentation | bar: 2017-01-23 to 2017-02-27
Post Implementation | bar: 2017-02-27 to 2017-03-06
Resource
Project Manager
Infrastructure Architect
System Analyst
Analyst Programmer
Resource Allocation
Project Manager | 2016-11-14: 39
System Analyst | 2016-11-14: 411
Analyst Programmer | 2016-11-14: 152.5

## Breakdown(Phase I)
Phase I - Man day Breakdown
Task | Project Manager | System Architect | System Analyst | Systems Analyst | Deliverable | Remarks
Project Management
Project Coordination, Project Tracking and Status Reporting | 30 |  |  |  | Project Related Documents - Please refer to Phase II
Migration Planning and Environment Assessment
Site Discovery / Environment Assessment |  |  |  | 2
Migration Planning, Identify Business and Technical Requirement |  |  |  | 5
Migration Plan Definition
Development Migration Plan |  |  |  | 8
Develop Migration Test Plan and Testing Guidelines |  |  |  | 5
Migration Verification Process
Establish POC environment |  |  |  | 5
Conduct Migration and Functional Test |  |  |  | 10
Production Server Migration and Switch Over
Migration for Production |  |  |  | 5
Conduct Migration and Functional Test |  |  |  | 2
| 30 | 0 | 0 | 42
Assumption:

## Breakdown(Phase II)
Phase II - Man day Breakdown
Task | Project Manager | System Architect | System Analyst | System Analyst | Analyst Programmer |  | Deliverable | Remarks
Project Management
Meeting and communication | 15 | [6 empty] | For coordinate with CX HK's infrastructure vendor, coordinate with business teams for UAT and prototype approval, coordinate with IT security for security test, coordinate with capacity team for load test, coordinate with external network vendor to setup new VPN. Communication overhead: infrastructure and network vendor: HW set and OAT (9 weeks x 1 MD) business team: SA&D; UAT; Impl (8 weeks x 0.5 MD) IT security / Capacity team: 2 MD
Prepare PMP | 2 | [5 empty] | 1) Project Management Plan (D) 2) High Level Project Schedule (D)(T) | Review project / contract scope, includes draft and revision.
Progress Monitoring and Control | 16 | [5 empty] | 7) Issue Log (D) (T) 8) Risk Log (D) (T) 10) Project Status Summary (D)(T) 11) Change Request Form (D) (T) 12) Change Request Log (D) (T) | One day per week to oversee the project progress, risk and issues. (including report progress)
Post Implementation Review / Report; Maintenance Transition | 2 | [6 empty] | For document learn learnt, project wrapup, and maintenance transition (4 x 0.5 day)
Other PM related documentation | 3 | [5 empty] | 3) Process Usage Plan (D)(T) 4) Configuration Management Plan (CMP) (D)(T) 5) Configurable Item Register (CIR) (D)(T) 6) Physical & Functional CM Audit Checklist (D)(T) 9) Quality Dashboard (D)(T) | 0.5 MD each
Environment Setup
Prepare Development Environment |  |  | 4 | 4 |  |  | Dev environment (Vendor) | VM x 2 (1 x MD) on-shore VM x 2 (1 x MD) off-shore
Prepare Test Environment (SIT and UAT) - Installation and configuration, hardening, documentation |  | 6 | 3 | 9 |  |  | SIT and UAT environment (CX) | SIT: VM x 4 (2 x MD) UAT: VM x 4 (1 x MD, leverage the SIT configure) Each set of environment cost 1.5 MD SA to take notes as manual
System Analysis and Design
Migration Planning (Change Analysis) |  | 6 | 9 | 15 |  |  |  | 6 Potential Topics 1.5 MD each for SA, 1 MD each for architect
Migration Planning (Review Potential Compatibility Issues within MQSeries with Solution) |  | 5 | 7.5 | 12.5 |  |  |  | 5 Potential Analysis Points, 1.5 MD each for SA, 1 MD each for architect
Migration Planning (Review Potential Compatibility Issues General Spotting) |  | 6 | 9 | 15 |  |  |  | 5 - 6 foreseen points, 1.5 MD each for SA, 1 MD each for architect
Review & Confirm Post-upgrade Change & Requirement |  | 2 | 2 | 4
Review and Confirm Requirements |  |  | 2 | 2 |  |  |  | Define requirements (functional and non-functional) catalogue and develop traceability matrix.
Design Walkthrough Workshop (2 workshops) |  |  | 2 | 2 |  |  |  | Including workshop material preparation, 1st workshop to review all UI, flows, I/O, etc., 2nd workshop for finalize the design
Produce System Design Specification |  |  | 3 | 3 |  |  | 13) System Design Specification (SDS) (D)(T) | Document technical solution, detailed requirements for database/ER modal, functional, non-functional. Provide recommendation on how other SMS/email application integrate to eNotification system
Review & Confirm System Design Specification |  |  | 3 | 3 | 1.5 |  |  | Consider 3 rounds for document walk through and confirmation
Produce Detail Migration Plan |  |  | 5 | 5 |  |  | 14) Migration Plan (MP) (D)(T)
Review & Confirm Detail Migration Plan |  |  | 2 | 2 | 1 |  |  | Consider 2 rounds for document walk through and confirmation
Produce Testing Strategy and Plan |  |  | 1 | 1 |  |  | 16) Unit Test Plan (D)(T)
Migration Implementation
Produce Technical Design Specification |  |  | 6 | 6 | 7 |  | 15) Technical Specification (TS) (D)(T) - Environment Configure 23) System Document(D) (T) - Environment Configure | Infra Arch x 2 days, need to conform to CX's security design and coding SA & AP takes around 10% documentation effort of the sum effort of implementation
Review & Confirm Technical Design Specification |  |  | 2 | 2 | 1 |  |  | Consider 2 rounds for document walk through and confirmation
Implement Queue Manager Clustering | [5 empty] | Implement MQ Configuration in SIT environment | Implement MQ Configuration in SIT environment | Implement MQ Configuration in SIT environment
Implement Queues - Remote/Alias (with Corp ESB - MB, Tuxedo Server, CXIP MQ, CXIP MB) & Unit Testing |  |  | 12 | 12 | 33 |  |  | Extra effort shall be needed for the coordination with 3rd Party Queue Manager owners 4 Queue Managers 14 Queue Manager Connections (2 Remote Cluster/MD to rebuild, 0.5 for SA to QA & verify the on-shore environment) 236 Remote Queues (10 Queues/MD to setup including communication, 0.3 for SA to QA and Follow up)
Implement Local Queue/Channel Configuration - Downline Application (DEV) | [7 empty] | 396 Local Queues 10-15 Queus/Day to Setup (0.3 for SA to QA and Follow up) 1 day/week for architect to QA work
Implement Local Queue/Channel Configuration - SITA Network (DEV) |  | 4 | 10 | 14 | 32
Channel Connectivity Test & Unit Testing |  | 6 | 15 | 21 | 30 |  |  | 236 Channels Est 5-6 Channels/Day (0.5 for SA to QA and Follow up)
Channel Performance Test (Middleware as blackbox)
Check Point |  |  | 1 | 1 | 1 |  |  | Prepare the environment for Application Team to participate, and conduct their own connectivity test and unit testing.
Deploy to SIT environment |  |  |  |  | 2
Draft Integration Test Plan |  |  | 1 | 1 |  |  | 17) System & Integration Test Plan (D)(T) - Draft
System Integration Test
Produce Integration Test Plan & Acceptance Criteria |  |  | 5 | 5 | 24 |  | 17) System & Integration Test Plan (D)(T) | The integration test would be mainly focus on the regression for all existing channels. 236 Channels, consider 1 MD for test cases for each 10 channels. And 20% for SA to review the test plan
Support End-to-End System Integration Test upon all Regression Cases |  |  | 236 | 118 |  |  |  | Assuming CX's IT managed to coordinate the application teams and plan for UAT, RGP mainly assists in providing technology supports and/or certain documentation of below items for each channels - Log & Sub-system monitoring (0.5) - Communication (0.5)
Deploy to UAT environment |  |  | 1 | 1 | 1
IT Acceptance Test
Define Acceptance Criteria |  |  | 1 | 1 | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
Support usability test |  |  | 1 | 1 | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
User Acceptance Test
Define Acceptance Criteria |  |  | 2 | 2 | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
Prepare UAT Plan (by CX) | [6 empty] | 20) UAT Test Plan (D) (T)
Training Material (Operations, Administration & Housekeeping) |  |  | 4 | 4 |  |  | 24) Training Document (D) (T) | Assuming leveraging User Manual's content to produce the training material
Conduct Training Sessions (Technical, Operation & Housekeeping) |  |  | 3 | 3 |  |  |  | Provides training to internal technical staffs, operation staffs and business on the new system, in terms of the operation, administration and reporting. Assumed TWO skill transfer sessions for technical and operation staffs, in presentation format (one-way), could illursate the operations and administration steps side-by-side. Assume ONE train-the-trainer session for business users. 0.5 day for one session, thus total 0.5 x 3 = 1.5 MD
Conduct and Support UAT |  |  | 236 | 118 |  |  | 21) UAT Defect Log (D) (T) 22) UAT Acceptance Form (D)(T) | Assuming CX's IT managed to coordinate the business users and plan for UAT, RGP mainly assists in providing technology supports and/or certain documentation of below items - Log & Sub-system monitoring (0.5) - Communication (0.5)
Prepare Operational Manual |  |  | 1 | 1 |  |  | 25) Operational Manual (D)
Prepare Administration Guides (Installation and Configuration) |  |  | 1 | 1
Prepare User Manual (Technical, Operation and Business) |  |  | 3 | 3 |  |  |  | Assuming provides scenarios based guide for each user role, and with how-to-use format to describe each user interface. No online help will be provided.(on average 1 MD each, so 1 x 3 = 3 MD
Performance and Penetration Test (MQSeries as Black Box)
Prepare performance test cases and scripts |  |  | 5 | 5 | 10
Perform performance test |  |  | 4.5 | 4.5 | 3 |  | 19) System Performance Report (D)(T) | Assuming at least one week (SA: 5 x 0.5 days) to conduct performance test, including tuning (AP: 3 days), and finalizing the performance report (SA: 2 days)
Operation Acceptance Test
Conduct OAT (including Resilience (HA) and Disaster recovery (DR) Test |  | 2 |  | 2 |  |  | 26) Review Form (D)(T)
Implementation
Prepare Implementation Plan |  |  | 2 | 2 |  |  | 27) Implementation Plan (D) (T) 28) Project QA Checklist (D)(T) | Prepare, review at least twice, and final work through.
Production Setup Implementation |  | 1 | 1 | 2 |  |  | 29) Release Request Form (D)(T)
Documentation
System Manual |  |  | 2 | 2 |  |  | 23) System Document(D) (T)
Post Implementation
Maintenance Transition | 1 |  | 1 | 1 |  |  | 30) Knowledge Transfer Review Checklist (D)(T)
| 39 | 38 | 609 | 411 | 152.5
Assumption:

## Deliverable (hidden)
Testing
Penetration Test
System Test
System Integration Test
Resilience (HA) Test
Disaster recovery (DR) Test
IT Accpetance Test
User Accpetance Test
Performance Test
Deliverables
Project Management
1) Project Management Plan (D)
2) High Level Project Schedule (D)(T)
3) Process Usage Plan (D)(T)
4) Configuration Management Plan (CMP) (D)(T)
5) Configurable Item Register (CIR) (D)(T)
6) Physical & Functional CM Audit Checklist (D)(T)
7) Issue Log (D) (T)
8) Risk Log (D) (T)
9) Quality Dashboard (D)(T)
10) Project Status Summary (D)(T)
11) Change Request Form (D) (T)
12) Change Request Log (D) (T)
System Design
13) System Design Specification (FS) (D)(T)
14) Detail Migration Plan (MP) (D)(T)
15) Technical Specification (TS) (D)(T)
System Implementation
16) Unit Test Plan (D)(T)
System Integration Test
17) System & Integration Test Plan (D)(T)
18) System & Integration Test Defect Log (D)(T)
19) System Performance Report (D)(T)
User Acceptance Test
20) UAT Test Plan (D) (T)
21) UAT Defect Log (D) (T)
22) UAT Acceptance Form (D)(T)
Documentation
23) System Document(D) (T)
24) Training Document (D) (T)
25) Operational Manual (D)
26) Review Form (D)(T)
Production Implementation
27) Implementation Plan (D) (T)
28) Project QA Checklist (D)(T)
29) Release Request Form (D)(T)
Post Implementation / Maintenance Support
30) Knowledge Transfer Review Checklist (D)(T)