## Summary
Manday Summary Sheet
Resource Allocation | Man-days (Breakdown) | Man-hours (Man-day x 8) | Man-Hours (Resources Calender) | Rate per hours (HKD)
Team Lead - Edward Leung | 73 | 584 | 584 | 560 | 327040
Systems Analyst - Tommy Leung | 341.5 | 2732 | 1448 | 510 | 738480
Systems Analyst - Eric Oei |  |  | 1284 | 510 | 654840
Systems Analyst - Off Shore - Lotic Lin | 79.5 | 636 | 636 | 460 | 292560
Analysis Programmer - Off Shore - Parko Lam | 226 | 1808 | 1128 | 300 | 338400
Analysis Programmer - Off Shore - Benjamin Cai |  |  | 680 | 300 | 204000
|  |  |  | HKD | 2555320
*The project is term and material basis.
*Service paid by completion of predefined phase (User Requirement Sign Off, SIT Sign Off and UAT Sign Off, etc)
*Cathay Pacific (CX) will allocate testing team to carry out end to end testing during SIT/UAT phasese, The project team will provide
minimal on-site and off-site support to CX during the testing period

## Timeline and Est (hidden)
Project Schedule
| Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul
| 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17
High Level Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W32
Project Initialization | bar: 2016-12-05
Hardware / Env / VPN Setup | bar: 2016-12-05 to 2016-12-19
Planning, Impact & Change Analysis,Technical Req | bar: 2016-12-05 to 2017-01-23
System Development | bar: 2016-12-26 to 2017-03-06
Unit Test & System Test | bar: 2017-01-23 to 2017-03-20
System Integration Test | bar: 2017-02-27 to 2017-05-15
User Acceptance Test | bar: 2017-03-27 to 2017-06-12
Operation Acceptance Test | bar: 2017-02-27 to 2017-04-17
Capacity, Performance and Penetration Test | bar: 2017-05-22 to 2017-06-12
Training/Knowledge Transfer | bar: 2017-05-22
Implementation | bar: 2017-06-19
Documentation | bar: 2017-05-22 to 2017-06-26
Post Implementation | bar: 2017-06-26 to 2017-07-17
Resources Calendar
Project Managers | 3 | 3 | 4 | 0 | 4 | 4 | 2 | 2 | 0 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 73
Systems Analyst - All | 5.5 | 7 | 7 | 0 | 8 | 11 | 11 | 12 | 0 | 13 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 5 | 5 | 5 | 327.5
Systems Analyst - On Shore - Steven Chen | 5 | 5 | 5 | 0 | 5 | 4 | 4 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 138
Systems Analyst - On Shore - Eric Wong | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 127
Systems Analyst - Off Shore | 0.5 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 61.5
Analysis Programmer I - Off Shore | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 98
Analysis Programmer II - Off Shore | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Project Managers | 24 | 24 | 32 | 0 | 32 | 32 | 16 | 16 | 0 | 8 | 8 | 8 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 584
Systems Analyst - All | 44 | 56 | 56 | 0 | 64 | 88 | 88 | 96 | 0 | 104 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 88 | 88 | 40 | 40 | 40 | 2620
Systems Analyst - On Shore - Steven Chen | 40 | 40 | 40 | 0 | 40 | 32 | 32 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 1104
Systems Analyst - On Shore - Eric Wong | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 1016
Systems Analyst - Off Shore | 4 | 16 | 16 | 0 | 24 | 24 | 24 | 24 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 492
Analysis Programmer I - Off Shore | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 784
Analysis Programmer II - Off Shore | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560
Resource Allocation
Systems Analyst - All | 2016-12-05: 421
Systems Analyst - On Shore - Steven Chen | 2016-12-05: 138
Systems Analyst - On Shore - Eric Wong | 2016-12-05: 127
Systems Analyst - Off Shore | 2016-12-05: 61.5
Analysis Programmer Off Shore - All | 2016-12-05: 1344
Analysis Programmer I Off Shore | 2016-12-05: 560
Analysis Programmer II Off Shore | 2016-12-05: 784
* Holiday on week of 26th Dec 2016 (put zero) in planning
* Holiday on week of 30th Jan 2017 (put zero) in planning

## Breakdown
Man day Breakdown
Task | Team Lead | System Analyst | SA Onshore | SA Off shore | Analyst Programmer | Application Owner | Deliverable | Remarks
Project Management
Meeting and communication | 45 | [6 empty] | For coordinate with CX HK's infrastructure vendor, coordinate with business teams for UAT and prototype approval, coordinate with IT security for security test, coordinate with capacity team for load test, coordinate with external network vendor to setup new VPN. Communication overhead: infrastructure and network vendor: HW set and OAT (9 weeks x 1 MD) business team: SA&D; UAT; Impl (8 weeks x 0.5 MD) IT security / Capacity team: 2 MD
Prepare PMP | 5 | [5 empty] | 1) Project Management Plan (D) 2) High Level Project Schedule (D)(T) | Review project / contract scope, includes draft and revision.
Progress Monitoring and Control | 16 | [5 empty] | 7) Issue Log (D) (T) 8) Risk Log (D) (T) 10) Project Status Summary (D)(T) 11) Change Request Form (D) (T) 12) Change Request Log (D) (T) | One day per week to oversee the project progress, risk and issues. (including report progress)
Post Implementation Review / Report; Maintenance Transition | 3 | [6 empty] | For document learn learnt, project wrapup, and maintenance transition (4 x 0.5 day)
Other PM related documentation | 3 | [5 empty] | 3) Process Usage Plan (D)(T) 4) Configuration Management Plan (CMP) (D)(T) 5) Configurable Item Register (CIR) (D)(T) 6) Physical & Functional CM Audit Checklist (D)(T) 9) Quality Dashboard (D)(T) | 0.5 MD each
Environment Setup
Prepare Development Environment |  | 4 | 1 | 3 |  |  | Dev environment (Vendor) | VM x 2 (1 x MD) on-shore VM x 2 (1 x MD) off-shore
Prepare Test Environment (SIT and UAT) - Installation and configuration, hardening, documentation |  | 9 | 9 |  |  |  | SIT and UAT environment (CX) | SIT: VM x 4 (2 x MD) UAT: VM x 4 (1 x MD, leverage the SIT configure) Each set of environment cost 1.5 MD SA to take notes as manual
Basic Testing MQ / Queue / Cluster Setup |  | 3 |  | 3 | 6
Basic Environment Testing |  | 2 |  | 2 | 4
System Analysis and Design
Application information Inquire |  | 15 | 15
Migration Planning (Change Analysis) |  | 15 | 10 | 5 |  |  |  | 6 Potential Topics 1.5 MD each for SA, 1 MD each for architect | Assume the list of application is ready
Migration Planning (Change Analysis) (FabriCX MQ) |  | 5 | 3 | 2 |  |  |  | Review whther the Corp MQ and FabriCX MQ has architecture difference. If yes then the MQ instances configuration will be impacted
Migration Planning (Review Potential Compatibility Issues within MQSeries with Solution) |  | 12.5 | 12.5 |  |  |  |  | 5 Potential Analysis Points, 1.5 MD each for SA, 1 MD each for architect
Migration Planning (Review Potential Compatibility Issues General Spotting) |  | 15 | 15 |  |  |  |  | 5 - 6 foreseen points, 1.5 MD each for SA, 1 MD each for architect
Migration Planning (Review Potential Compatibility Issues within MQSeries with Solution) FabriCX MQ |  | 4 | 4 |  |  |  |  | Add leveraged man days to include the 100 queus for FabriCX MQ Est. Add up 30% for the overhead including studying a brand new MQSeries
Migration Planning (Review Potential Compatibility Issues General Spotting) FabriCX MQ |  | 4.5 | 4.5 |  |  |  |  | Add leveraged man days to include the 100 queus for FabriCX MQ. Est. Add up 30% for the overhead including studying a brand new MQSeries
Review & Confirm Post-upgrade Change & Requirement |  | 5 | 5
Review and Confirm Change & Requirements |  | 3 | 2 | 1 |  |  |  | Define requirements (functional and non-functional) catalogue and develop traceability matrix.
Design Walkthrough Workshop (2 workshops) |  | 2 | 2 |  |  |  |  | Including workshop material preparation, 1st workshop to review all UI, flows, I/O, etc., 2nd workshop for finalize the design
Design Walkthrough Workshop (1-2 workshops) FabriCX MQ |  | 2 | 2 |  |  |  |  | Assume the FabriCX MQ is annother owner/sponser and requires another round of walk through and revision
Produce System Design Specification |  | 5 | 5 |  |  |  | 13) System Design Specification (SDS) (D)(T) | ToC provided in the deliverable list
Writing System Design Specification (FabriCX MQ) |  | 1.5 | 1.5 |  |  |  | 13) System Design Specification (SDS) (D)(T) | ToC provided in the deliverable list
Review & Confirm System Design Specification |  | 3 | 3 |  | 2 |  |  | Consider 3 rounds for document walk through and confirmation
Review & Confirm System Design Specification (FabriCX MQ) |  | 2 | 2 |  |  |  |  | Consider 2 rounds for document walk through and confirmation (different owner)
Produce Detail Migration Plan |  | 5 | 2 | 3 |  |  | 14) Migration Plan (MP) (D)(T)
Produce Detail Migration Plan (FabriCX MQ) |  | 2 | 1 | 1 |  |  | 14) Migration Plan (MP) (D)(T) | Consider 100 queues and communication overhead
Review & Confirm Detail Migration Plan |  | 5 | 2 | 3 |  |  |  | Consider 3 rounds for document walk through and confirmation 2 MD for AP Revision
Produce Unit Test Plan |  | 3 | 0 | 3 |  |  | 16) Unit Test Plan (D)(T)
Review Unit Test Plan |  | 2 | 2 | 0
Migration Implementation
Produce Technical Design Specification |  | 6 | 6 |  | 7 |  | 15) Technical Specification (TS) (D)(T) - Environment Configure 23) System Document(D) (T) - Environment Configure | Infra Arch x 2 days, need to conform to CX's security design and coding SA & AP takes around 10% documentation effort of the sum effort of implementation
Produce Technical Design Specification (FabriCX MQ) |  | 1.5 | 1.5 |  | 2 |  | 15) Technical Specification (TS) (D)(T) - Environment Configure 23) System Document(D) (T) - Environment Configure | 100 queues technical document effort + 20 % communication overhead
Review & Confirm Technical Design Specification |  | 2 | 2 |  | 1 |  |  | Consider 2 rounds for document walk through and confirmation
Implement Queue Manager Clustering | [6 empty] | Implement MQ Configuration in SIT environment | Implement MQ Configuration in SIT environment
Implement Queues - Remote/Alias (with Corp ESB - MB, Tuxedo Server, CXIP MQ, CXIP MB) & Unit Testing |  | 8 | 4 | 4 | 16 |  |  | Extra effort shall be needed for the coordination with 3rd Party Queue Manager owners 4 Queue Managers 14 Queue Manager Connections (2 Remote Cluster/MD to rebuild, 0.5 for SA to QA & verify the on-shore environment) 236 Remote Queues (10 Queues/MD to setup including communication, 0.3 for SA to QA and Follow up)
Implement Local Queue/Channel Configuration - Downline Application (DEV) | [7 empty] | 396 Local Queues 10-15 Queus/Day to Setup (0.3 for SA to QA and Follow up) 1 day/week for architect to QA work
Implement Local Queue/Channel Configuration - SITA Network (DEV) |  | 14 | 7 | 7 | 32
Implement Queues - FabriCX MQ & Unit Testing Assumption: 1/3 Local Queus, 1/3 Alias/Remote queues, 1/3 Complex Channels with Request-Response, Publish/Subscribe |  | 4 | 4 |  | 12
Channel Connectivity Test & Unit Test |  | 12 | 2 | 10 | 20 |  |  | 236 Channels Est 10-15 Channels/Day (0.5 for SA to QA and Follow up) | Write script / program to test
Channel Connectivity Test & Unit Test (FabricCX MQ) Assume around 50 Channel |  | 3 | 1 | 2 | 5 |  |  | 236 Channels Est 10-15 Channels/Day (0.5 for SA to QA and Follow up) | Write script / program to test
Check Point |  | 2 | 1 | 1 | 2 |  |  | Prepare the environment for Application Team to participate, and conduct their own connectivity test and unit testing.
Deploy to SIT environment |  | 5 | 5 |  | 10
Deploy to SIT environment (FabriCX MQ) |  | 1 | 1 |  | 2
System Integration Test (MQ Series as Black Box)
Produce Integration Test Plan & Acceptance Criteria |  | 5 | 2 | 3 | 11 |  | 17) System & Integration Test Plan (D)(T) | The integration test would be mainly focus on the regression for all existing channels. 236 Channels, consider 1 MD for test cases for each 10 channels. And 20% for SA to review the test plan
Produce Integration Test Plan & Acceptance Criteria (FabriCX MQ) |  | 1 |  | 1 | 3 |  | 17) System & Integration Test Plan (D)(T) | The integration test would be mainly focus on the regression for all existing channels. 236 Channels, consider 1 MD for test cases for each 10 channels. And 20% for SA to review the test plan
Conduct System Integration Test (Driven by CorpMQ Message Sender & Receiver) upon Sample Cases below - Client Connection Type - Local/Remote QM - Communication Pattern - Sender & Receiver |  | 36 | 24 | 12 | 48 |  |  | Assuming CX's IT managed to coordinate the application teams to test message throughputs via dummy clients including Java JMS, C, MainFrame and AS/400 , RGP mainly assists in providing technology supports and/or certain documentation of below items - Each types of channel x each types of traffic. 4MD x 4 x 2(Sender/Receiver) - Remote Queue Managers (2 MD x 8 Pairs) - Communication Overhead(50%) - 80 Cases Included
Conduct System Integration Test (FabricCX MQ) |  | 9 | 6 | 3 | 12 |  |  | Assumpt 50 Channels and with 4 cases each. Conducting 15 cases/day - Communication Overhead(50%)
Deploy to UAT environment |  | 10 | 5 | 5 | 5
IT Acceptance Test
Define Acceptance Criteria |  | 1 | 1 |  | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
Support Acceptance Test |  | 1 | 1 |  | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
User Acceptance Test Support (End-to-End) | [6 empty] | UAT refers to the end-to-end regression testing which starts from user/operation. This test may not be performed by user but CX IT or Testing Team to conduct an automated test upon full regression cases of in scope interfaces
Define Acceptance Criteria |  | 2 | 2 |  | 2 |  |  | Conduct with CX's Middleware Team (1 session only).
Prepare UAT Plan (by CX) | [6 empty] | 20) UAT Test Plan (D) (T)
Review UAT Plan |  | 3 | 3
Training Material (Operations, Administration & Housekeeping) |  | 4 | 2 | 2 |  |  | 24) Training Document (D) (T) | Assuming leveraging User Manual's content to produce the training material
Conduct UAT Briefing &Training (Technical highlights, Testing Approach) |  | 3 | 3 |  |  |  |  | Provides training to internal & external application teams in terms of the application technical highlights, and Testing Approach & Cycles.Assume THREE session for all relevant parties. 0.5 day for one session, and 0.5 of preparation 1 x 3 = 3 MD
Conduct and Support UAT (Driven by End Users) |  | 88.5 | 88.5 |  |  |  | 21) UAT Defect Log (D) (T) 22) UAT Acceptance Form (D)(T) | Assuming CX's IT managed to coordinate the business users and plan for UAT, RGP mainly assists in providing technology supports and/or certain documentation of below items - Log & Sub-system monitoring (0.25) - Communication overhead (50% of lum sum)
Conduct and Support UAT (Driven by End Users) |  | 20 | 20 |  |  |  | 21) UAT Defect Log (D) (T) 22) UAT Acceptance Form (D)(T) | Assuming 50 Channels for FabriCX MQ - Log & Sub-system monitoring (0.25) - Communication overhead (50% of lum sum)
Prepare Operational Manual |  | 1 | 1 |  | 3 |  | 25) Operational Manual (D)
Prepare Administration Guides (Installation and Configuration) |  | 2 | 2 |  | 2
Performance and Penetration Test (MQSeries as Black Box)
Prepare performance test cases and scripts |  | 2 | 1 | 1 | 6 |  |  | 2 MD - MDB 2 MD Traffic Loading Sender-Receiver 2 Queue & Subsystem Monitoring Job 30% for SA Supervision & QA
Perform performance test |  | 4.5 | 4.5 |  | 5 |  | 19) System Performance Report (D)(T) | Assuming at least one week (SA: 5 x 0.5 days) to conduct performance test (AP: 5 days), and finalizing the performance report (SA: 2 days)
Full Regression Test | [7 empty] | (Assume: With Testing Script Provided)
Conduct the Regresion Test | [7 empty] | Appx 130 Application
Code Change
Devolopment |  | 0 | 0 |  | 0
Unit Test |  | 0 | 0 |  | 0
Operation Acceptance Test
Prepare OAT Cases (including Resilience (HA) Test) |  | 2 | 2 |  |  |  | 26) Operation Acceptance Test Cases
Conduct OAT Testing |  | 4 | 4 |  |  |  | 26) Operation Acceptance Test Report | Scope of OAT - Resilience (HA) - Cluster Failover (Stop/Re-start) - 8 Main Cases Included
Implementation
Prepare Implementation Plan |  | 2 | 1 | 1 | 4 |  | 27) Implementation Plan (D) (T) 28) Project QA Checklist (D)(T) | Prepare, review 2 rounds, and final work through.
Production Setup Implementation |  | 6 | 6 |  |  |  | 29) Release Request Form (D)(T) | Depend on actual channel release phases, 2 MD for each phase and assume 3 phases are required
Documentation
Review and Confirm Operational Manual |  | 3 | 1.5 | 1.5 |  |  | 25) Operational Manual (D) | Revision 2MD, 2 Rounds Review
Post Implementation
Maintenance Transition | 1 | 3 | 3 |  |  |  | 30) Knowledge Transfer Review Checklist (D)(T)
Post Implementation Support |  | 20 | 20
| 73 | 421 | 341.5 | 79.5 | 226
Assumption: | 584 | 3368 | 2732 | 636 | 1808

## Resources Calendar
Project Schedule
High Level Project Timeline
Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Project Initialization | bar: Week 1
Hardware / Env / VPN Setup | bar: Week 1 to Week 3
| SA1 | Week 1: 1; Week 2: 4; Week 3: 5
SA2 | bar: Week 1 to Week 3
| SAF | Week 1: 3; Week 2: 3; Week 3: 2
| AP1 | Week 2: 3; Week 3: 2
| AP2 | Week 2: 3; Week 3: 2
Application information Inquire | bar: Week 1 to Week 9
| SA | Week 1: 1; Week 2: 1; Week 3: 1; Week 4: 1; Week 5: 1; Week 6: 2; Week 7: 2; Week 8: 3; Week 9: 3
Planning, Impact & Change Analysis, Technical Req | bar: Week 1 to Week 13
| SA1 | Week 4: 5; Week 5: 3; Week 6: 5; Week 7: 5; Week 8: 5; Week 9: 5; Week 10: 5; Week 11: 5; Week 12: 5; Week 13: 2.5
| SA2 | Week 3: 2; Week 10: 5; Week 11: 5; Week 12: 5
| SAF | Week 3: 3; Week 13: 5
| AP1 | Week 5: 2
AP2 | bar: Week 1 to Week 13
System Development | bar: Week 4 to Week 14
SA1 | bar: Week 4 to Week 14
| SA2 | Week 4: 2; Week 5: 1; Week 6: 2; Week 7: 2; Week 8: 2; Week 9: 2
| SAF | Week 4: 2; Week 5: 1; Week 6: 2; Week 7: 2; Week 8: 2; Week 9: 2
| AP1 | Week 4: 5; Week 5: 5; Week 6: 5; Week 7: 5; Week 8: 5; Week 9: 5
| AP2 | Week 6: 5; Week 7: 5; Week 8: 5; Week 9: 5
Unit Test & System Test | bar: Week 8 to Week 16
SA2 | bar: Week 8 to Week 16
| SAF | Week 10: 5; Week 11: 5; Week 12: 1
| AP1 | Week 10: 5; Week 11: 5; Week 12: 1
| AP2 | Week 10: 5; Week 11: 5; Week 12: 1
Code Change | bar: Week 10 to Week 23
| SA | Week 10: 5; Week 11: 5; Week 12: 5; Week 13: 5; Week 14: 5; Week 15: 5; Week 16: 5; Week 17: 5; Week 18: 10; Week 19: 5; Week 20: 5; Week 21: 5; Week 22: 5; Week 23: 5
| AP | Week 10: 10; Week 11: 10; Week 12: 10; Week 13: 10; Week 14: 20; Week 15: 20; Week 16: 20; Week 17: 20; Week 18: 10; Week 19: 10; Week 20: 10; Week 21: 10
SIT Deployment | bar: Week 14
| AP | Week 14: 5
System Integration Test | bar: Week 15 to Week 27
| SAO | Week 15: 4; Week 16: 4; Week 17: 0; Week 18: 2; Week 19: 2; Week 20: 2; Week 21: 2; Week 22: 2; Week 23: 2; Week 24: 2; Week 25: 2; Week 26: 2; Week 27: 2
| SAF | Week 15: 4; Week 16: 1; Week 17: 1; Week 18: 1; Week 19: 1; Week 20: 1; Week 21: 1; Week 22: 1; Week 23: 1; Week 24: 1; Week 25: 1; Week 26: 1; Week 27: 1
| AP | Week 15: 5; Week 16: 5; Week 17: 0; Week 18: 5; Week 19: 5; Week 20: 5; Week 21: 5; Week 22: 5; Week 23: 5; Week 24: 5; Week 25: 5; Week 26: 5; Week 27: 5
Prepare UAT Plan By CX | bar: Week 10 to Week 19
User Acceptance Test Setup | bar: Week 17
User Acceptance Test | bar: Week 20 to Week 31
Operation Acceptance Test | bar: Week 15 to Week 22
Full Regression Test | bar: Week 18 to Week 31
Capacity, Performance and Penetration Test | bar: Week 28 to Week 31
Training/Knowledge Transfer | bar: Week 32
Implementation | bar: Week 36
Documentation | bar: Week 32 to Week 37
Post Implementation | bar: Week 37 to Week 40
Resources Calendar
Team Lead - Edward Leung |  | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 73 | 73 | Team Lead | 73 | 73 | 0
Systems Analyst - Tommy Leung |  | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 1 | 1 | 1 | 181 | 341.5 | Systems Analyst - On Shore | 290 | 341.5 | 51.5
Systems Analyst - Eric Oei |  | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0.5 | 0 | 0 | 0 | 160.5 |  |  |  |  | 0
Systems Analyst - Off Shore |  | 0.5 | 3 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 79.5 | 79.5 | Systems Analyst - Off Shore | 70.5 | 79.5 | 9
Analysis Programmer I - Off Shore - Parko Lam |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 141 | 226 | Analyst Programmer - Off Shore | 190 | 226 | 36
Analysis Programmer II - Off Shore - Benjamin Cai |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85
Team Lead - Edward Leung |  | 24 | 24 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 584
Systems Analyst - Tommy Leung |  | 24 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 8 | 8 | 8 | 8 | 1448
Systems Analyst - Eric Oei |  | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 4 | 0 | 0 | 0 | 1284
Systems Analyst - Off Shore - Lotic Lin |  | 4 | 24 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 40 | 16 | 16 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 636
Analysis Programmer - Off Shore - Parko Lam |  | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1128
Analysis Programmer - Off Shore - Benjamin Cai |  | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680

## Deliverable (hidden)
Testing
Penetration Test
System Test
System Integration Test
Resilience (HA) Test
Disaster recovery (DR) Test
IT Accpetance Test
User Accpetance Test
Performance Test
Deliverables
Project Management
1) Project Management Plan (D)
2) High Level Project Schedule (D)(T)
3) Process Usage Plan (D)(T)
4) Configuration Management Plan (CMP) (D)(T)
5) Configurable Item Register (CIR) (D)(T)
6) Physical & Functional CM Audit Checklist (D)(T)
7) Issue Log (D) (T)
8) Risk Log (D) (T)
9) Quality Dashboard (D)(T)
10) Project Status Summary (D)(T)
11) Change Request Form (D) (T)
12) Change Request Log (D) (T)
System Design
13) System Design Specification (FS) (D)(T)
14) Detail Migration Plan (MP) (D)(T)
15) Technical Specification (TS) (D)(T)
System Implementation
16) Unit Test Plan (D)(T)
System Integration Test
17) System & Integration Test Plan (D)(T)
18) System & Integration Test Defect Log (D)(T)
19) System Performance Report (D)(T)
User Acceptance Test
20) UAT Test Plan (D) (T)
21) UAT Defect Log (D) (T)
22) UAT Acceptance Form (D)(T)
Documentation
23) System Document(D) (T)
24) Training Document (D) (T)
25) Operational Manual (D)
26) Review Form (D)(T)
Production Implementation
27) Implementation Plan (D) (T)
28) Project QA Checklist (D)(T)
29) Release Request Form (D)(T)
Post Implementation / Maintenance Support
30) Knowledge Transfer Review Checklist (D)(T)