## Sheet1
Cost Estimation - CX Server Upgrade
Background
Task carried out by Billy company. On top of the man-day added by him, add PM and related testing
Cost Estimation
Task Description | PM/SA/AP |  | Remarks | Billy | Man-day
Project Management | PM |  | Buzz IT PM to CX
Project Management | INFRA | #REF! | Project Coordination and Status Reporting (Billy Side) | Yes | 6
Discovery | INFRA | #REF! | Site Discovery | Yes | 2
Discovery | INFRA | #REF! | Migration Plan | Yes | 5
Definition | INFRA |  | Development Migration Plan | Yes | 1
Definition | INFRA |  | Develop Migration Test Plan and Testing Guidelines | Yes
Construction | INFRA |  | Establish POC environment | Yes | 5
Construction | INFRA |  | Conduct Migration and Functional Test | Yes | 5
Delivery | INFRA |  | Migration for Production | Yes
Delivery | INFRA |  | Conduct Migration and Functional Test | Yes | 5
Unit Test | AP | #REF! | Unit testings on related changes - Buzz IT |  | 2
Documentation | SA | #REF! | Documentations to CX - System Diagram |  | 2
|  |  | Total Manday (PM) |  | 2
|  |  | Total Manday (INFRA) |  | 29
Total Manday (SA)
|  |  | Total Manday |  | 31
* AP - Analyst Programmer
* SA - System Analyst
* PM - Project Manager
* INFRA - Infra-structure Engineer