## Summary
Manday Summary Sheet
Resource Allocation | Man-day | Man-hour | Rate per hours (HKD)
Team Lead | 73 | 584 | 560 | 327040
Systems Analyst - On Shore | 321.5 | 2572 | 510 | 1311720
Systems Analyst - Off Shore | 70.5 | 564 | 460 | 259440
Analyst Programmer - Off Shore | 350 | 2800 | 300 | 840000
Testing Team Manager - Off Shore | 30 | 240 | 350 | 84000
Testing Team Members (4) | 260 | 2080 | 300 | 624000
|  |  | HKD | 3446200
*The project is term and material basis.
*Service paid by completion of predefined phase (User Requirement Sign Off, SIT Sign Off and UAT Sign Off, etc)
*Cathay Pacific (CX) will allocate testing team to carry out end to end testing during SIT/UAT phasese, The project team will provide
minimal on-site and off-site support to CX during the testing period

## Timeline and Est (hidden)
Project Schedule
| Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul
| 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17
High Level Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W32
Project Initialization | bar: 2016-12-05
Hardware / Env / VPN Setup | bar: 2016-12-05 to 2016-12-19
Planning, Impact & Change Analysis,Technical Req | bar: 2016-12-05 to 2017-01-23
System Development | bar: 2016-12-26 to 2017-03-06
Unit Test & System Test | bar: 2017-01-23 to 2017-03-20
System Integration Test | bar: 2017-02-27 to 2017-05-15
User Acceptance Test | bar: 2017-03-27 to 2017-06-12
Operation Acceptance Test | bar: 2017-02-27 to 2017-04-17
Capacity, Performance and Penetration Test | bar: 2017-05-22 to 2017-06-12
Training/Knowledge Transfer | bar: 2017-05-22
Implementation | bar: 2017-06-19
Documentation | bar: 2017-05-22 to 2017-06-26
Post Implementation | bar: 2017-06-26 to 2017-07-17
Resources Calendar
Project Managers | 3 | 3 | 4 | 0 | 4 | 4 | 2 | 2 | 0 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 73
Systems Analyst - All | 5.5 | 7 | 7 | 0 | 8 | 11 | 11 | 12 | 0 | 13 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 5 | 5 | 5 | 327.5
Systems Analyst - On Shore - Steven Chen | 5 | 5 | 5 | 0 | 5 | 4 | 4 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 138
Systems Analyst - On Shore - Eric Wong | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 127
Systems Analyst - Off Shore | 0.5 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 61.5
Analysis Programmer I - Off Shore | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 98
Analysis Programmer II - Off Shore | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Project Managers | 24 | 24 | 32 | 0 | 32 | 32 | 16 | 16 | 0 | 8 | 8 | 8 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 584
Systems Analyst - All | 44 | 56 | 56 | 0 | 64 | 88 | 88 | 96 | 0 | 104 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 88 | 88 | 40 | 40 | 40 | 2620
Systems Analyst - On Shore - Steven Chen | 40 | 40 | 40 | 0 | 40 | 32 | 32 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 1104
Systems Analyst - On Shore - Eric Wong | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 1016
Systems Analyst - Off Shore | 4 | 16 | 16 | 0 | 24 | 24 | 24 | 24 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 492
Analysis Programmer I - Off Shore | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 784
Analysis Programmer II - Off Shore | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560
Resource Allocation
Systems Analyst - All | 2016-12-05: 372
Systems Analyst - On Shore - Steven Chen | 2016-12-05: 138
Systems Analyst - On Shore - Eric Wong | 2016-12-05: 127
Systems Analyst - Off Shore | 2016-12-05: 61.5
Analysis Programmer Off Shore - All | 2016-12-05: 1344
Analysis Programmer I Off Shore | 2016-12-05: 560
Analysis Programmer II Off Shore | 2016-12-05: 784
* Holiday on week of 26th Dec 2016 (put zero) in planning
* Holiday on week of 30th Jan 2017 (put zero) in planning

## Breakdown
Phase II - Man day Breakdown
Task | Project Manager | System Architect | System Analyst | System Analyst | SA Onshore | SA Off shore | Analyst Programmer | Testing Manager | Testing Team | Application Owner | Deliverable | Remarks
Project Management
Meeting and communication | 45 | [10 empty] | For coordinate with CX HK's infrastructure vendor, coordinate with business teams for UAT and prototype approval, coordinate with IT security for security test, coordinate with capacity team for load test, coordinate with external network vendor to setup new VPN. Communication overhead: infrastructure and network vendor: HW set and OAT (9 weeks x 1 MD) business team: SA&D; UAT; Impl (8 weeks x 0.5 MD) IT security / Capacity team: 2 MD
Prepare PMP | 5 | [9 empty] | 1) Project Management Plan (D) 2) High Level Project Schedule (D)(T) | Review project / contract scope, includes draft and revision.
Progress Monitoring and Control | 16 | [9 empty] | 7) Issue Log (D) (T) 8) Risk Log (D) (T) 10) Project Status Summary (D)(T) 11) Change Request Form (D) (T) 12) Change Request Log (D) (T) | One day per week to oversee the project progress, risk and issues. (including report progress)
Post Implementation Review / Report; Maintenance Transition | 3 | [10 empty] | For document learn learnt, project wrapup, and maintenance transition (4 x 0.5 day)
Other PM related documentation | 3 | [9 empty] | 3) Process Usage Plan (D)(T) 4) Configuration Management Plan (CMP) (D)(T) 5) Configurable Item Register (CIR) (D)(T) 6) Physical & Functional CM Audit Checklist (D)(T) 9) Quality Dashboard (D)(T) | 0.5 MD each
Environment Setup
Prepare Development Environment |  |  | 4 | 4 | 1 | 3 |  |  |  |  | Dev environment (Vendor) | VM x 2 (1 x MD) on-shore VM x 2 (1 x MD) off-shore
Prepare Test Environment (SIT and UAT) - Installation and configuration, hardening, documentation |  | 6 | 3 | 9 | 9 | [5 empty] | SIT and UAT environment (CX) | SIT: VM x 4 (2 x MD) UAT: VM x 4 (1 x MD, leverage the SIT configure) Each set of environment cost 1.5 MD SA to take notes as manual
Basic Testing MQ / Queue / Cluster Setup | [5 empty] | 3 | 6
Basic Environment Testing | [5 empty] | 2 | 4
System Analysis and Design
Application information Inquire |  |  |  |  | 15
Migration Planning (Change Analysis) |  | 6 | 9 | 15 | 10 | 5 | [5 empty] | 6 Potential Topics 1.5 MD each for SA, 1 MD each for architect | Assume the list of application is ready
Migration Planning (Review Potential Compatibility Issues within MQSeries with Solution) |  | 5 | 7.5 | 12.5 | 12.5 | [6 empty] | 5 Potential Analysis Points, 1.5 MD each for SA, 1 MD each for architect
Migration Planning (Review Potential Compatibility Issues General Spotting) |  | 6 | 9 | 15 | 15 | [6 empty] | 5 - 6 foreseen points, 1.5 MD each for SA, 1 MD each for architect
Review & Confirm Post-upgrade Change & Requirement |  | 2 | 2 | 5 | 5
Review and Confirm Change & Requirements |  |  | 2 | 3 | 2 | 1 | [5 empty] | Define requirements (functional and non-functional) catalogue and develop traceability matrix.
Design Walkthrough Workshop (2 workshops) |  |  | 2 | 2 | 2 | [6 empty] | Including workshop material preparation, 1st workshop to review all UI, flows, I/O, etc., 2nd workshop for finalize the design
Produce System Design Specification |  |  | 3 | 5 | 5 | [5 empty] | 13) System Design Specification (SDS) (D)(T) | Document technical solution, detailed requirements for database/ER modal, functional, non-functional. Provide recommendation on how other SMS/email application integrate to eNotification system
Review & Confirm System Design Specification |  |  | 3 | 3 | 3 |  | 2 |  |  |  |  | Consider 3 rounds for document walk through and confirmation
Produce Detail Migration Plan |  |  | 5 | 5 | 2 | 3 |  |  |  |  | 14) Migration Plan (MP) (D)(T)
Review & Confirm Detail Migration Plan |  |  | 2 | 5 | 2 | 3 | [5 empty] | Consider 3 rounds for document walk through and confirmation 2 MD for AP Revision
Produce Unit Test Plan |  |  | 1 | 3 | 0 | 3 |  |  |  |  | 16) Unit Test Plan (D)(T)
Review Unit Test Plan |  |  |  | 2 | 2 | 0
Migration Implementation
Produce Technical Design Specification |  |  | 6 | 6 | 6 |  | 7 |  |  |  | 15) Technical Specification (TS) (D)(T) - Environment Configure 23) System Document(D) (T) - Environment Configure | Infra Arch x 2 days, need to conform to CX's security design and coding SA & AP takes around 10% documentation effort of the sum effort of implementation
Review & Confirm Technical Design Specification |  |  | 2 | 2 | 2 |  | 1 |  |  |  |  | Consider 2 rounds for document walk through and confirmation
Implement Queue Manager Clustering | [10 empty] | Implement MQ Configuration in SIT environment | Implement MQ Configuration in SIT environment
Implement Queues - Remote/Alias (with Corp ESB - MB, Tuxedo Server, CXIP MQ, CXIP MB) & Unit Testing |  |  | 12 | 8 | 4 | 4 | 16 |  |  |  |  | Extra effort shall be needed for the coordination with 3rd Party Queue Manager owners 4 Queue Managers 14 Queue Manager Connections (2 Remote Cluster/MD to rebuild, 0.5 for SA to QA & verify the on-shore environment) 236 Remote Queues (10 Queues/MD to setup including communication, 0.3 for SA to QA and Follow up)
Implement Local Queue/Channel Configuration - Downline Application (DEV) | [11 empty] | 396 Local Queues 10-15 Queus/Day to Setup (0.3 for SA to QA and Follow up) 1 day/week for architect to QA work
Implement Local Queue/Channel Configuration - SITA Network (DEV) |  | 4 | 10 | 14 | 7 | 7 | 32
Channel Connectivity Test & Unit Test |  | 2 | 15 | 12 | 2 | 10 | 20 |  |  |  |  | 236 Channels Est 10-15 Channels/Day (0.5 for SA to QA and Follow up) | Write script / program to test
Check Point |  |  | 1 | 2 | 1 | 1 | 2 |  |  |  |  | Prepare the environment for Application Team to participate, and conduct their own connectivity test and unit testing.
Deploy to SIT environment |  |  |  | 5 | 5 |  | 10
System Integration Test (MQ Series as Black Box)
Produce Integration Test Plan & Acceptance Criteria |  |  | 5 | 5 | 2 | 3 | 11 |  |  |  | 17) System & Integration Test Plan (D)(T) | The integration test would be mainly focus on the regression for all existing channels. 236 Channels, consider 1 MD for test cases for each 10 channels. And 20% for SA to review the test plan
Conduct System Integration Test (Driven by CorpMQ Message Sender & Receiver) upon Sample Cases below - Client Connection Type - Local/Remote QM - Communication Pattern - Sender & Receiver |  |  | 236 | 36 | 24 | 12 | 48 |  |  |  |  | Assuming CX's IT managed to coordinate the application teams to test message throughputs via dummy clients including Java JMS, C, MainFrame and AS/400 , RGP mainly assists in providing technology supports and/or certain documentation of below items - Each types of channel x each types of traffic. 4MD x 4 x 2(Sender/Receiver) - Remote Queue Managers (2 MD x 8 Pairs) - Communication Overhead(50%) - 80 Cases Included
Deploy to UAT environment |  |  | 1 | 10 | 5 | 5 | 5
IT Acceptance Test
Define Acceptance Criteria |  |  | 1 | 1 | 1 |  | 2 |  |  |  |  | Conduct with CX's Middleware Team (1 session only).
Support Acceptance Test |  |  | 1 | 1 | 1 |  | 2 |  |  |  |  | Conduct with CX's Middleware Team (1 session only).
User Acceptance Test (End-to-End)
Define Acceptance Criteria |  |  | 2 | 2 | 2 |  | 2 |  |  |  |  | Conduct with CX's Middleware Team (1 session only).
Prepare UAT Plan (by CX) | [10 empty] | 20) UAT Test Plan (D) (T)
Review UAT Plan |  |  |  | 3 | 3
Training Material (Operations, Administration & Housekeeping) |  |  | 4 | 4 | 2 | 2 |  |  |  |  | 24) Training Document (D) (T) | Assuming leveraging User Manual's content to produce the training material
Conduct UAT Briefing &Training (Technical highlights, Testing Approach) |  |  | 3 | 3 | 3 | [6 empty] | Provides training to internal & external application teams in terms of the application technical highlights, and Testing Approach & Cycles.Assume THREE session for all relevant parties. 0.5 day for one session, and 0.5 of preparation 1 x 3 = 3 MD
Conduct and Support UAT (Driven by End Users) |  |  | 236 | 50 | 50 | [5 empty] | 21) UAT Defect Log (D) (T) 22) UAT Acceptance Form (D)(T) | Assuming CX's IT managed to coordinate the business users and plan for UAT, RGP mainly assists in providing technology supports and/or certain documentation of below items - Log & Sub-system monitoring (0.25) - Communication overhead (50% of lum sum)
Prepare Operational Manual |  |  | 1 | 1 | 1 |  | 3 |  |  |  | 25) Operational Manual (D)
Prepare Administration Guides (Installation and Configuration) |  |  | 1 | 2 | 2 |  | 2
Performance and Penetration Test (MQSeries as Black Box)
Prepare performance test cases and scripts |  |  | 5 | 2 | 1 | 1 | 6 |  |  |  |  | 2 MD - MDB 2 MD Traffic Loading Sender-Receiver 2 Queue & Subsystem Monitoring Job 30% for SA Supervision & QA
Perform performance test |  |  | 4.5 | 4.5 | 4.5 |  | 5 |  |  |  | 19) System Performance Report (D)(T) | Assuming at least one week (SA: 5 x 0.5 days) to conduct performance test (AP: 5 days), and finalizing the performance report (SA: 2 days)
Full Regression Test | [11 empty] | (Assume: With Testing Script Provided)
Conduct the Regresion Test | [7 empty] | 30 | 260 |  |  | Appx 130 Application
Code Change
Devolopment |  |  |  | 50 | 50 |  | 100
Unit Test |  |  |  | 20 | 20 |  | 60
Operation Acceptance Test
Prepare OAT Cases (including Resilience (HA) Test) |  | 2 |  | 2 | 2 | [5 empty] | 26) Operation Acceptance Test Cases
Conduct OAT Testing |  | 2 |  | 4 | 4 | [5 empty] | 26) Operation Acceptance Test Report | Scope of OAT - Resilience (HA) - Cluster Failover (Stop/Re-start) - 8 Main Cases Included
Implementation
Prepare Implementation Plan |  |  | 2 | 2 | 1 | 1 | 4 |  |  |  | 27) Implementation Plan (D) (T) 28) Project QA Checklist (D)(T) | Prepare, review 2 rounds, and final work through.
Production Setup Implementation |  | 1.5 | 1 | 6 | 6 | [5 empty] | 29) Release Request Form (D)(T) | Depend on actual channel release phases, 2 MD for each phase and assume 3 phases are required
Documentation
Review and Confirm Operational Manual |  |  | 2 | 3 | 1.5 | 1.5 |  |  |  |  | 25) Operational Manual (D) | Revision 2MD, 2 Rounds Review
Post Implementation
Maintenance Transition | 1 |  | 1 | 3 | 3 | [5 empty] | 30) Knowledge Transfer Review Checklist (D)(T)
Post Implementation Support |  |  |  | 20 | 20
| 73 | 36.5 | 605 | 372 | 321.5 | 70.5 | 350 | 30 | 260
Assumption: |  |  |  | 2976 | 2572 | 564 | 2800 | 240 | 2080

## 工作表1
Project Schedule
High Level Project Timeline |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39
Project Initialization | bar: W1
Hardware / Env / VPN Setup | bar: W1 to W3
| SA1 | W1: 1; W2: 4; W3: 5
SA2 | bar: W1 to W3
| SAF | W1: 3; W2: 3; W3: 2
| AP1 | W2: 3; W3: 2
| AP2 | W2: 3; W3: 2
Application information Inquire | bar: W1 to W9
| SA | W1: 1; W2: 1; W3: 1; W4: 1; W5: 1; W6: 2; W7: 2; W8: 3; W9: 3
Planning, Impact & Change Analysis,Technical Req | bar: W1 to W13
| SA1 | W4: 5; W5: 3; W6: 5; W7: 5; W8: 5; W9: 5; W10: 5; W11: 5; W12: 5; W13: 2.5
| SA2 | W3: 2; W10: 5; W11: 5; W12: 5
| SAF | W3: 3; W13: 5
| AP1 | W5: 2
AP2 | bar: W1 to W13
System Development | bar: W4 to W14
SA1 | bar: W4 to W14
| SA2 | W4: 2; W5: 1; W6: 2; W7: 2; W8: 2; W9: 2
| SAF | W4: 2; W5: 1; W6: 2; W7: 2; W8: 2; W9: 2
| AP1 | W4: 5; W5: 5; W6: 5; W7: 5; W8: 5; W9: 5
| AP2 | W6: 5; W7: 5; W8: 5; W9: 5
Unit Test & System Test | bar: W8 to W16
SA2 | bar: W8 to W16
| SAF | W10: 5; W11: 5; W12: 1
| AP1 | W10: 5; W11: 5; W12: 1
| AP2 | W10: 5; W11: 5; W12: 1
Code Change | bar: W10 to W23
| SA | W10: 5; W11: 5; W12: 5; W13: 5; W14: 5; W15: 5; W16: 5; W17: 5; W18: 10; W19: 5; W20: 5; W21: 5; W22: 5; W23: 5
| AP | W10: 10; W11: 10; W12: 10; W13: 10; W14: 20; W15: 20; W16: 20; W17: 20; W18: 10; W19: 10; W20: 10; W21: 10
SIT Deployment | bar: W14
| AP | W14: 5
System Integration Test | bar: W15 to W27
| SAO | W15: 4; W16: 4; W17: 0; W18: 2; W19: 2; W20: 2; W21: 2; W22: 2; W23: 2; W24: 2; W25: 2; W26: 2; W27: 2
| SAF | W15: 4; W16: 1; W17: 1; W18: 1; W19: 1; W20: 1; W21: 1; W22: 1; W23: 1; W24: 1; W25: 1; W26: 1; W27: 1
| AP | W15: 5; W16: 5; W17: 0; W18: 5; W19: 5; W20: 5; W21: 5; W22: 5; W23: 5; W24: 5; W25: 5; W26: 5; W27: 5
Prepare UAT Plan By CX | bar: W10 to W19
User Acceptance Test Setup | bar: W17
User Acceptance Test | bar: W20 to W31
Operation Acceptance Test | bar: W15 to W22
Full Regression Test | bar: W18 to W31
Capacity, Performance and Penetration Test | bar: W28 to W31
Training/Knowledge Transfer | bar: W32
Implementation | bar: W35
Documentation | bar: W32 to W36
Post Implementation | bar: W36 to W39
Resources Calendar
Project Managers |  | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 73
Systems Analyst - All |  | 3.5 | 8 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 10 | 13 | 11 | 11 | 15 | 9 | 9 | 12 | 12 | 11 | 11 | 8 | 8 | 8 | 9 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 8 | 6 | 6 | 6 | 6 | 371.5
Systems Analyst - On Shore - Steven Chen |  | 3 | 5 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 185
Systems Analyst - On Shore - Eric Wong |  | 0 | 0 | 0 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 4 | 4 | 5 | 2 | 2 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 116
Systems Analyst - Off Shore |  | 0.5 | 3 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 70.5
Analysis Programmer I - Off Shore |  | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 10 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 190
Analysis Programmer II - Off Shore |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160
Testing Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Testing Team |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260
Team Lead |  | 24 | 24 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 584
Systems Analyst - All |  | 28 | 64 | 80 | 80 | 80 | 80 | 80 | 96 | 96 | 96 | 96 | 96 | 80 | 104 | 88 | 88 | 120 | 72 | 72 | 96 | 96 | 88 | 88 | 64 | 64 | 64 | 72 | 64 | 64 | 64 | 64 | 64 | 56 | 56 | 56 | 64 | 48 | 48 | 48 | 48 | 2972
Systems Analyst - On Shore - Tommy Leung |  | 24 | 40 | 40 | 40 | 40 | 32 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 40 | 24 | 24 | 24 | 24 | 1480
Systems Analyst - On Shore - Eric Wong |  | 0 | 0 | 0 | 24 | 24 | 32 | 32 | 40 | 40 | 40 | 40 | 40 | 24 | 24 | 32 | 32 | 40 | 16 | 16 | 40 | 40 | 40 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 928
Systems Analyst - Off Shore |  | 4 | 24 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 40 | 16 | 16 | 40 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 564
Analysis Programmer I - Off Shore |  | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 80 | 40 | 40 | 40 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 1520
Analysis Programmer II - Off Shore |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280
Testing Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240
Testing Team |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 120 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080
Resource Allocation
Systems Analyst - All |  | W1: 372
Systems Analyst - On Shore - Steven Chen |  | W1: 185
Systems Analyst - On Shore - Eric Wong |  | W1: 116
Systems Analyst - Off Shore |  | W1: 70.5
Analysis Programmer Off Shore - All |  | W1: 2800
Analysis Programmer I Off Shore |  | W1: 1520
Analysis Programmer II Off Shore |  | W1: 1280
Testing Manager |  | W1: 240
Testing Team |  | W1: 2080

## Deliverable (hidden)
Testing
Penetration Test
System Test
System Integration Test
Resilience (HA) Test
Disaster recovery (DR) Test
IT Accpetance Test
User Accpetance Test
Performance Test
Deliverables
Project Management
1) Project Management Plan (D)
2) High Level Project Schedule (D)(T)
3) Process Usage Plan (D)(T)
4) Configuration Management Plan (CMP) (D)(T)
5) Configurable Item Register (CIR) (D)(T)
6) Physical & Functional CM Audit Checklist (D)(T)
7) Issue Log (D) (T)
8) Risk Log (D) (T)
9) Quality Dashboard (D)(T)
10) Project Status Summary (D)(T)
11) Change Request Form (D) (T)
12) Change Request Log (D) (T)
System Design
13) System Design Specification (FS) (D)(T)
14) Detail Migration Plan (MP) (D)(T)
15) Technical Specification (TS) (D)(T)
System Implementation
16) Unit Test Plan (D)(T)
System Integration Test
17) System & Integration Test Plan (D)(T)
18) System & Integration Test Defect Log (D)(T)
19) System Performance Report (D)(T)
User Acceptance Test
20) UAT Test Plan (D) (T)
21) UAT Defect Log (D) (T)
22) UAT Acceptance Form (D)(T)
Documentation
23) System Document(D) (T)
24) Training Document (D) (T)
25) Operational Manual (D)
26) Review Form (D)(T)
Production Implementation
27) Implementation Plan (D) (T)
28) Project QA Checklist (D)(T)
29) Release Request Form (D)(T)
Post Implementation / Maintenance Support
30) Knowledge Transfer Review Checklist (D)(T)