## Slide 1: Project Approach

## Slide 2
PROJECT APPROACH
Step 1 – Feasibility Study | 
PURPOSE | To Identify New Requirements/Changes on New Features (Optional) To Investigate interfaces specification of all endpoints/clients, in order to come up risk managed planning and approach To identify housekeeping processes in existing middleware To facilitate and development team to complete PoC on new version of MQ Clients Connection
KEY ACTVITIES | Work closely with middleware team to study technical documents or operation manuals of existing middleware Collect and study the interface documents of the client applications Identify the complexity and materiality level of all channels upon serving different application domains
Impact Analysis
Dependencies of existing interfaces and MQ features
Critical Compatibility Issues
Identification of relevant systems by application owners
DELIVERABLES
Feasibility Report
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
Project Initiation
Step 1
Feasibility Study

## Slide 3
PROJECT APPROACH
Step 2 – Project Initiation | 
PURPOSE | To study and identify technical dependency on critical business applications and infrastructure To determine current recovery time of critical business applications and infrastructure To identify relationship between critical business processes and applications and infrastructure
KEY ACTVITIES | Identify key stakeholders of all related channels Compile dependency matrix on critical IT systems
DELIVERABLES
Project Plan
… filled by Edward
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
Project Initiation
Step 1
Feasibility Study

## Slide 4
PROJECT APPROACH
Step 3 – System Analysis and Migration Planning | 
PURPOSE | To Identify New Requirements/Changes on New Features (Optional) To Investigate interfaces specification of all endpoints/clients, in order to come up a less risky planning to To identify housekeeping processes in existing middleware To facilitate and development team to complete PoC on new version of MQ Clients Connection
KEY ACTVITIES | Work closely with middleware team to study technical documents or operation manuals of existing middleware Collect and study the interface documents of the client applications Provide support to application development team to conduct the PoC Document middleware architecture and configuration
DELIVERABLES
System Implementation Document
System Architecture
MQ Configuration
  Clusters Design
  QMs, Queues, Channels
  Logging, Housekeeping
HA and Disaster Recovery
Related Interfaces/Messages
Migration Phases Planning
Compatibility Issues and Consideration
Requirement Change Management
Channel/Interface Prioritization
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
System Analysis
Step 1
Feasibility Study
Migration Plan

## Slide 5
PROJECT APPROACH
Step 4 – Migration Execution | 
PURPOSE | To Implement the MQ Configuration To Collect testing results on the basis of the test plan To Perform smoke test and connectivity test with dummy clients
KEY ACTVITIES | Implement the development of the WebSphere MQ and Message Broker Develop dummy endpoints to conduct System Test Develop a simple utility to perform volume test and collect testing results Extend the test cases if supplementary test is required.
DELIVERABLES
System Test Plan & Results
Performance Results
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
System Analysis
Step 1
Feasibility Study

## Slide 6
PROJECT APPROACH
Step 4 – Migration Execution | 
PURPOSE | To implement the new version of MQ Servers By phases to allow System Users perform the end-to-end testing with all systems involved
KEY ACTVITIES | Provide support to system user and their testing teams All related parties monitor their responsible components Monitor the stability, performance and issues of MQ Server during the testing
DELIVERABLES
SIT Test Plan and Test Result
SIT Defect Log
SIT Sign-off
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
System Analysis
Step 1
Feasibility Study
Acceptance Criteria
UAT Test Plan and Test Result
UAT Defect Log
UAT Sign-off

## Slide 7
PROJECT APPROACH
Step 6
Deployment
Step 5
System Integration Test
Step 4
Migration Implementation
Step 3
Migration Planning
Step2
System Analysis
Step 1
Feasibility Study
Step 6 – Middleware Deployment and Post-Production Support | 
PURPOSE | To ensure the deliverables quality and stability in production environment
KEY ACTVITIES | Deploy the MQ to production environment Post-deployment smoke test on all channel interfaces Monitor the end-to-end processing of the implemented interfaces
DELIVERABLES
Deployment Manual – details of the deployments steps, checks points, roll back procedures, with deployment scripts as appendix.
Deployment procedure
Deployment Steps
  Detail commands
  Check points
  Rollback procedures