## AIX
WBS# | Task
Manday
Project Management
1.1 | Project Coordination | 6
1.2 | Project Tracking and Status Reporting
Discovery Phase
2.1 | Site Discovery Conduct assessment to current Infrastruction: - AIX P6 and P7+ Environment - Network Infrastructure - Backup and Recovery Environment - Storage Infrastructure | 2
2.2 | Migration Plan Identify business and technical requirements: - Migration Requirement - AIX Compatibility - Migration Methodology | 5
Definition Phase
3.1 | Develop Migration Plan | 5
3.3 | Develop Migration Test Plan and Testing Guidelines | 2
Construction Phase
4.1 | Establish POC environment | 5
4.2 | Conduct Migration and Functional Test | 5
Devlivery Phase
5.1 | Migration for Production | 5
5.2 | Conduct Migration and Functional Test | 2
37
Remark:
1 | Application Compatibility or code change not included
2 | Application Perfromenace Not included
3 | Storage/SAN Migration not includede