## Workplan
|  |  |  | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31
|  |  |  | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Task |  |  | Deliverable
Discover Queue Information
| Discover Fabric MQ Manager (as-is) |  | Queue Inventory | bar: 2017-02-21 to 2017-02-24; 2017-02-27 to 2017-02-28
Detailed Queue Information | bar: 2017-02-21 to 2017-02-24; 2017-02-27 to 2017-02-28
| Discover DMZ MQ Manager (as-is) |  | Queue Inventory
Detailed Queue Information
| Discover Corp MQ Manager (as-is) |  | Queue Inventory
Detailed Queue Information
| Define Fabric MQ Manager (to-be) |  | Queue Inventory
Detailed Queue Information
| Define DMZ MQ Manager (to-be) |  | Queue Inventory
Detailed Queue Information
| Define Corp MQ Manager (to-be) |  | Queue Inventory
Detailed Queue Information
Checkpoint for discuss and review?
Discover Application MQ Connection
Design Application Survey Form
|  | Review Form Sample | Blank form | bar: 2017-02-24
|  | Review Pre-filled Form Sample | Pre-filled form | bar: 2017-02-27
|  | Revise and Confirm Form | Pre-filled form | bar: 2017-02-27 to 2017-02-28
| Prepare Pre-filled Form for Application team |  | Owner XXXX
Owner XXXX
Owner XXXX
Conduct briefing to Application Team
| Distribute Survey Form |  | Pre-filled form
Review first round feedback
Conduct individual interview with Application Team
Review final round feedback
Conduct individual interview with Application Team
| Prepare Application MQ Connection Inventory |  | Application MQ Connection Inventory
System Architecture Diagram
| Draft High level Diagram |  | MQ Manager level diagram
Fabric MQ
DMZ MQ
Corp MQ
Review High level Diagram
| Draft Application level Diagram |  | Application level diagram
Application for Owner XXXX
Application for Owner XXXX
Application for Owner XXXX
Application for Owner XXXX
Application for Owner XXXX
Application for Owner XXXX
Discover Application Test Case Coverage
| Prepare the Application MQ test case matrix |  | Application MQ Testing Case coverage
Review the Application MQ test case matrix
Recommond High level migration plan and schedule |  |  | High level migration plan and schedule
Prepare Discovery Report
| Review draft |  | Discovery Report
| Submit final |  | Discovery Report (final)

## Application Survey PF
Design Survey Form
Application Team Briefing
- Project Objective
- Purpose of the Survey
- Application Team Involvement
- Timeline
- Contact
Distribute Survey Form to Application Owners
Collect first round feedback
e.g. - Question on survey form
- Have difficulty to fill up
Collect final round feedback
Conduct individual interview
Conduct individual interview (supplement on missing areas)
Survey Form
(pre-filled)
Meeting
Email
Email
Meeting
Conf. Call
Email
Meeting
Conf. Call