## Issue List
Project Name: Maxim's ESB POS Polling Project |  |  | 34
UAT Issue List
# | Date | Issue Description | Module (e.g POS Polling, EDW, Others) | Severity (High, Medium, Low) | Category (Defect, CR, Info) | Follow Up | Expected Fixed Date | Remarks | Status (Open, Investigation, Resolved, Closed) | MD Used
1 | 6/14/2017 | Unexpected EOD Data | Polling/EDW | Low | Defect | Edward | 6/14/2017 | Patch Data Fix the Create Branch Script | Closed
2 | 6/14/2017 | Multiple Master Scheme in Different POS | Master | High | CR | Tommy | 6/30/2017 | Change Program | Closed | 3MD
3 | 6/14/2017 | Timeout Handling for Different Poll (Real Time / EOD / Master) | Polling | Medium | CR | Tommy | 6/30/2017 | Before is one Timeout for all Polling | Closed | 0.5MD
4 | 6/22/2017 | Incorrect Record Count show in the log | Polling | Medium | Defect | Lotic | 6/23/2017 | Fix the Program | Closed
5 | 6/27/2017 | Copy DBF to Local before upload to Server | Polling | Medium | CR | Tommy | 6/23/2017 | Performance will be much improved due to too much File in the share Path | Closed | 1MD
6 | 6/27/2017 | Enhance the Octopus File Copy | Polling | Medium | CR | Tommy | 6/23/2017 | Enchance to Simplifed the Config | Closed | 2MD
7 | 6/27/2017 | Dead Lock Issue for Serialization | Polling | Medium | Defect | Tommy | 7/24/2017 | Change Program | Closed
8 | 6/28/2017 | Fix the Pagination on Task Job Detail | Polling | Medium | Defect | Lotic | 6/30/2017 | Fix the Program | Closed
9 | 6/28/2017 | Enhance to add authentication on Web Service Call | Web Service | Medium | CR | Tommy | 7/7/2017 | Update in OSB | Closed | 1MD
10 | 6/28/2017 | Update the Stock Take Webservice | Stock Take | Medium | Procedure | Maxm | 7/3/2017 | Add patching to defer the stock take, and the webervice will be change on next week by maxim | Closed
11 | 6/28/2017 | High CPU SQL | Polling | Low | Enhancement | Tommy | 7/3/2017 | Add the index to improve the performance | Closed
12 | 7/4/2017 | Some Branch is Fail for EOD | Polling | Medium | CR | Tommy | 7/7/2017 | Due the network not stable for some POS Retry for intrim folustion and update the progrom to do the reconnection | Closed
13 | 7/5/2017 | Skip upload to Server if the DBF is the same | Polling | Low | CR | Tommy | 7/7/2017 | Change the program to skip indentical DBF | Closed | 0.5 MD
14 | 7/5/2017 | Missing some branch for conversion | conversion | Medium | Info | Maxim | 7/7/2017 | There are some missing branch when extract the branch converion batch | Closed
15 | 7/5/2017 | Add the default value if the timetamp field is null for DBF | Polling | Medium | CR | Tommy | 7/7/2017 | Change the program | Closed | 0.5MD
16 | 7/5/2017 | Enhance to Not proceed to EDW for any Fail during EOD | Polling | Medium | CR | Tommy | 7/7/2017 | Change the program | Closed | 0.25MD
17 | 7/5/2017 | Enhance to system to support SQL Server version > 2000 | Polling | Medium | CR | Tommy | 7/7/2017 | Change the program | Closed | 0.5MD
18 | 7/6/2017 | High CPU Using Due to Sybase Wrong Index is used | Polling | Medium | Defect | Maxim | 7/6/2017 | Update the SQL Server to use correct index for Query | Closed
19 | 7/6/2017 | Duplication Record in EDW | EDW | Medium | Defect | Tommy | 7/7/2017 | The srcKey / destKey value have a space and make the duplicaiton checking not work. Patch the Database and rerun all the Real Time Job from POS to Staging to EDW | Closed
20 | 7/6/2017 | Add reconnection logic during polling | Polling | Low | CR | Tommy | 7/7/2017 | Currently, the retry logic is done when initialized the connection to POS. However, there are some branch is not stable and always drop connection during polling We have add the logic to reconnect durong polling | Closed | 1MD
21 | 7/7/2017 | Duplication Key Error | Polling | Low | Defect | Tommy | 7/7/2017 | During UAT, the system is using the rowguid as the key. However, the rowguid will be change in POS even the same record We have update the key in Staging DB and update the database config value to avoiding it. | Closed
22 | 7/10/2017 | Missing Data in Staging but in EDW | Polling | Medium | Defect | Tomy | 7/10/2017 | The issue happen when stock take happen The program is updated and re-run all branch EOD since launch | Closed
23 | 7/10/2017 | Missing table for DBF EOD polling | Polling | Medium | CR | Tommy Maxim | 7/10/2017 | One more table is identifed to be upload for DBF during EOD There are some special logic after uplod the TRANS / Order Table We have build a newthe view to upload to EDW and the EDW will handle this logic during conversion Reun all the branch DBF EOD process | Closed | 0MD
24 | 7/10/2017 | Received an invalid column length from the bcp client | Polling | Medium | CR | Maxim | 7/10/2017 | Update the pos layout to avoid it | Closed
25 | 7/11/2017 | Master update error | Polling | Medium | Defect | Tommy Maxim | 7/11/2017 | During UAT, the system is using the rowguid as the key. This will cluase the duplication We have update the key in Staging DB and update the database config value to avoiding it. | Closed
26 | 7/11/2017 | Missing Record in EOD for SQL Server 2008 | Polling | Medium | Defect | Tommy | 7/11/2017 | The Bulk Copy may clause missing record We have add the record count checking before and after The task will be failed if not match | Closed
27 | 7/12/2017 | Missing EOD record DBF | Polling | Medium | Defect | Tommy | 7/10/2017 | The issue will happened when run multiple day during EOD All the DBF have rerun in Monday and find this issue. | Closed
28 | 7/13/2017 | Splitted Date recording missing in EDW | EDW | Medium | Defect | Tommy | 7/14/2017 | The splited record exists in staging only but not EDW The program is amend to fix it We have rerun all the branch with the splied date | Closed
29 | 7/13/2017 | Slow performance at night time (21:00) | Polling | Medium | Defect | Maxim | 7/14/2017 | The system is extreme slow during this period and find all the network throughput is used by other system We have montor the system, the system have resumed after the through put is normal Maxim will find out the cause of it | Closed
30 | 7/14/2017 | Remove the mandatory Checking in Web Service | Web Service | Medium | CR | Tommy Lotic | 7/24/2017 | Maxim asked to remove some mandatory checking for the web service | Open | 1MD
31 | 7/17/2017 | The amount generated in the splitted logic is not correct | Polling | Medium | Defect | Tommy | 7/17/2017 | Find out the correct logic with maxim and update the program | Closed
32 | 7/17/2017 | Stock Take File Error | Polling | Medium | CR | Maxim | 7/18/2017 | The Table in ST file will not all exists. Maxim will follow up what is the correct logic | Open
33 | 7/18/2017 | Add alert for Job Halt, there is a EOD job is keep pending in the system. | Polling | Medium | Defect | Tommy | 7/18/2017 | Change the program | Closed
34 | 7/20/2017 | Splitted Date Error for non Base ccy | Polling | Medium | Defect | Tommy | 7/20/2017 | Fix the program | Closed
33 | 7/20/2017 | For Master update, There are multiple POS client and user SQL Server merge replication for the distribution. We are using delete / insert method for the data replication thus, the rowguid will sync from master to pos as well However, the master and Pos client rowguid are different and the row guild will not work if master rowguid change | Polling | Medium | CR | Tommy | 7/24/2017 | Change the logic to update / delete and ignore the field rowguid for master update | Open | 2MD

## Statistics
Project Name: AXA e-Notification Project
UAT - Statistics
Count of Status (Open, Investigation, Resolved, Closed) | Column Labels
Row Labels | Grand Total
Grand Total