## WBS
Work Break Down on System Analysis and Design
Work Task | ID in Requirement Traceability Matrix | % of Completion | Section in System Design Document | Section in Technical Design Document | Section in Impact Analysis Report | Owner | From | To | Remarks
System Design Documentation |  | 0%
Architecture Design |  | 100% | 3 |  |  | Steven | 2017-01-04 | 2017-01-09 | Architecture Diagram / Description
Data Model Design |  | 70% | 4 |  |  | Steven, Lotic | 2017-01-04 | 2017-01-09 | ER Diagram (Non-Business only)
High Level Interface Design |  | 0% | 5 |  |  | Tommy | 2017-01-04 | 2017-01-09
Functional Design |  | 0% | 6
Sales Data Real Time polling to Staging DB (Job) | ESB-SAL-01 | 100% | 6.1 |  |  | Steven | 2017-01-04 | 2017-01-09
Sales Data Real Time - Data Processing to EDW (Job) | ESB-SAL-02 | 0% | 6.2 |  |  | Edward | 2017-01-04 | 2017-01-09
POS Client EOD Data Process (Job) | ESB-SAL-03 | 50% | 6.3 |  |  | Steven | 2017-01-04 | 2017-01-09
POS Client EOD Data Process - Data Processing to EDW (Job) | ESB-SAL-04 | 0% | 6.4 |  |  | Edward | 2017-01-04 | 2017-01-09
Pricing/Master Data Processing (Job) | ESB-PRZ-REQ-01 | 0% | 6.5 |  |  | Steven | 2017-01-04 | 2017-01-09
Pricing/Master Data Distribution (Job) | ESB-MST-REQ-02 | 0% | 6.6 |  |  | Steven | 2017-01-04 | 2017-01-09
System Setting - Poll Schema Maintenance (UI) | ESB-NF-REQ-01-08 | 50% | 7.8 |  |  | Steven | 2017-01-04 | 2017-01-09
System Setting - Branch Info Maintenance (UI) | ESB-NF-REQ-01-09 ESB-NF-REQ-01-02 ESB-NF-REQ-01-03 | 50% | 7.9 |  |  | Steven | 2017-01-04 | 2017-01-09
System Setting - Scheduler Jobs Maintenance (UI) | ESB-NF-REQ-01-09 | 0% | 7.9 |  |  | Steven | 2017-01-04 | 2017-01-09
Job Logs View (UI) | ESB-NF-REQ-01-01 | 0% | 7.1 |  |  | Tommy | 2017-01-04 | 2017-01-09
Non-functional Requirements | ESB-NF-REQ-01 | 0% | 7
System Dashboard View - Real Time (UI) | ESB-NF-REQ-01-01 | 0% | 7.1 |  |  | Steven | 2017-01-04 | 2017-01-09
System Exception Report - Jobs Process | ESB-NF-REQ-01-04 | 0% | 7.4 |  |  | Edward | 2017-01-04 | 2017-01-09
System Exception Report - Data Process | ESB-NF-REQ-01-05 | 0% | 7.5 |  |  | Edward | 2017-01-04 | 2017-01-09
System Exception Handling - Jobs Process | ESB-NF-REQ-01-06 | 0% | 7.6 |  |  | Tommy | 2017-01-04 | 2017-01-09
System Exception Handling - Data Process (EOD) | ESB-NF-REQ-01-07 | 0% | 7.7 |  |  | Tommy | 2017-01-04 | 2017-01-09
System Configuration (UI) | ESB-NF-REQ-01-10 | 0% | 7.10 |  |  | Steven | 2017-01-04 | 2017-01-09
ESB-NF-REQ-02 System Interface | ESB-NF-REQ-02 | 0% | 8
Sales Data Web Service | ESB-NF-REQ-02-01 | 100% | 8.1 |  |  | Tommy | 2017-01-04 | 2017-01-09
Pricing/Master Data DB Adapter | ESB-NF-REQ-02-02 | 100% | 8.2 |  |  | Tommy | 2017-01-04 | 2017-01-09
Sales Data DB Adapters - Total Number | ESB-NF-REQ-02-03 | 50% | 8.3 |  |  | Tommy | 2017-01-04 | 2017-01-09
Sales Data DB Adapters - Total Amount | ESB-NF-REQ-02-04 | 50% | 8.4 |  |  | Tommy | 2017-01-04 | 2017-01-09
Pricing/Master Data DB Adapter | ESB-NF-REQ-02-05 | 0% | 8.5 |  |  | Tommy | 2017-01-04 | 2017-01-09
Technical Design Documentation |  | 0%
Data Flows |  | 0% |  | 3
POS Client to Staging | ESB-SAL-01, 03 | 0% |  | 3.1 |  | Steven | 2017-01-09 | 2017-01-11
Staging to EDW | ESB-SAL-02, 04 | 0% |  | 3.2 |  | Tommy | 2017-01-09 | 2017-01-11
Data Model Design - Database Schema |  | 0% |  | 4
Business Data Related Tables (Diff Data Sources, POS clients, Staging Data Model, EDW Data) |  | 0% |  | 4.1 |  | Steven, Edward, Tommy | 2017-01-09 | 2017-01-11
Non-Business Data Model |  | 100% |  | 4.2 |  | Steven | 2017-01-09 | 2017-01-11 | received on 04-Jan
Application Log Configuration |  | 100% |  | 4.3 |  | Steven | 2017-01-09 | 2017-01-11
Job Control Specification |  | 0% |  | 5
6 Job Controllers Definition | ESB-SAL-01 to 04, ESB-PRZ-REQ-01, ESB-MST-REQ-02 | 0% |  | 5.1 |  | Steven | 2017-01-09 | 2017-01-11
Task Scheme Definition - Single Task Detail Flow | ESB-SAL-01 to 04, ESB-PRZ-REQ-01, ESB-MST-REQ-02 | 0% |  | 5.2 |  | Steven | 2017-01-09 | 2017-01-11
Sales Data Real Time polling to Staging DB | ESB-SAL-01 | 0% |  | 5.3 |  | Edward | 2017-01-09 | 2017-01-11
Sales Data Real Time - Data Processing to EDW | ESB-SAL-02 | 0% |  | 5.4 |  | Edward | 2017-01-09 | 2017-01-11
POS Client EOD Data Process | ESB-SAL-03 | 0% |  | 5.5 |  | Edward | 2017-01-09 | 2017-01-11
POS Client EOD Data Process - Data Processing to EDW | ESB-SAL-04 | 0% |  | 5.6 |  | Edward | 2017-01-09 | 2017-01-11
Pricing/Master Data Processing | ESB-PRZ-REQ-01 | 0% |  | 5.7 |  | Steven | 2017-01-09 | 2017-01-11
Pricing/Master Data Distribution | ESB-MST-REQ-02 | 0% |  | 5.8 |  | Steven | 2017-01-09 | 2017-01-11
Infrastructure |  | 0% |  | 6 |  | To be confirmed
Interface Clients Management | ESB-NF-REQ-02 | 0% |  | 7 |  | To be confirmed
UI Application Program Flows | ESB-NF-REQ-01-08, 09 | 0% |  | 8 |  | Parko | 2017-01-09 | 2017-01-11
Backup & Housekeeping |  | 0% |  | 9
History Table Data Purging / DB Log Full | TBC | 0% |  | 9.1 |  | Lotic | 2017-01-09 | 2017-01-11
DBF file / CSV file purging | TBC | 0% |  | 9.2 |  | Lotic | 2017-01-09 | 2017-01-11
OSB Log Files Removal | TBC | 0% |  | 9.3 |  | Lotic | 2017-01-09 | 2017-01-11
Database Backup (Oracle or SQLServer to be confirmed) | TBC | 0% |  | 9.4 |  | Lotic | 2017-01-09 | 2017-01-11
Impact Analysis & the Report |  | 0%
IT51/52/53 data flows |  | 0% |  |  | 3 | Steven, Edward, Tommy | 2017-01-12 | 2017-01-13
Plan implementation strategy I |  | 0% |  |  | 4 | Steven, Edward, Tommy | 2017-01-12 | 2017-01-13
Plan implementation strategy II |  | 0% |  |  | 5 | Steven, Edward, Tommy | 2017-01-12 | 2017-01-13
Contingency |  | 0% |  |  | 6 | Steven, Edward, Tommy | 2017-01-12 | 2017-01-13
Work-Around Approach |  | 0% |  |  | 7 | Steven, Edward, Tommy | 2017-01-12 | 2017-01-13

## Req Traceability Matrix
Requirement Traceability Matrix
ID | Name | Description | By | Priority | Owner | Parent
ESB-SAL-01 | Sales Data Real Time polling to Staging DB | Collect the sales data in POS clients to Service Bus Staging DB in real time. | Edward | Must Have | Carl
ESB-SAL-01-01 | Sales Data Real Time - Data staging to service bus working DB - Scheduling | In real time, the service bus shall trigger schedule jobs to download data from POS clients’ database. | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-01-02 | Sales Data Real Time - Data staging to service bus working DB - Database Types | The schedule job shall handle 2 kinds of data source connection according to different POS machine vendors. | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-01-03 | Sales Data Real Time - Data staging to service bus working DB - Transaction Handling - Mitpos | The service bus polling application will take care of the sales order transactions according to different POS client. - MITPOS | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-01-04 | Sales Data Real Time - Data staging to service bus working DB - Transaction Handling - Pointsoft | The service bus polling application will take care of the sales order transactions according to different POS client. - POINTSOFT | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-01-05 | Sales Data Real Time - Update POS Client’s Polling Flag after | Update POS Client’s Polling Flag after the download of data is successful. | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-01-06 | Sales Data Real Time - Polling to Staging DB Job Completion | The job completion shall log information of the job processing in DB for real time processing. | Edward | Must Have | Carl | ESB-SAL-01
ESB-SAL-02 | Sales Data Real Time - Data Processing to EDW | Send sales data to EDW Service Bus Staging DB in real time. | Edward | Must Have | Polly
ESB-SAL-02-01 | Sales Data Real Time - Data Processing to EDW - Check Data Integrity (MIDPOS & POINTSOFT) | The real time sales data processing job (Staging to EDW) reads sales data from Staging DB. Firstly, it shall check the Data integrity for data from both MIDPOS and POINTSOFT. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-02-02 | Sales Data Real Time - Data Processing to EDW - Retrieve Table List for Checking (Check_log, Orders..) | Data processing job will focus on real time sales data related target table. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-02-03 | Sales Data Real Time - Data Processing to EDW - Send Data to EDW after verification | After verifying whether the sales data is completed. Send the completed data to EDW. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-02-04 | Sales Data Real Time - Data Processing to EDW - Exceptional Handling | Real Time sales data polling exceptional data handling. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-02-05 | Sales Data Real Time - Data Processing to EDW - Data Send Block by Block | Sales data sending, by block update and return code. With the return code of the service call, the process will mark the block of records the completion of the sending to EDW. When return value is a failure code, the process applies a retry mechanism with the retry limit. If the number of retry exceeds the limit, it shall skip to next block, and the job will end with error data log. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-02-06 | Sales Data Real Time - Data Processing to EDW Job Completion | The job completion shall log information of the job processing in DB for real time processing. | Edward | Must Have | Polly | ESB-SAL-02
ESB-SAL-03 | POS Client EOD Data Process | Collect the sales data in POS clients to Service Bus Staging DB for End of Day process (EOD) | Edward | Must Have | Carl
ESB-SAL-03-01 | POS Client EOD Triggering | After the POS client completes its EOD processing, it insert a new record into ”hist_possystem“ table indicating it’s ready for the EOD polling. | Edward | Must Have | Carl | ESB-SAL-03
ESB-SAL-03-02 | POS Client EOD Monitoring | The service bus shall run an application monitoring the local end-of-day indicator in the POS database. | Edward | Must Have | Carl | ESB-SAL-03
ESB-SAL-03-03 | POS Client EOD Data Process - Download all History Tables | The service bus initiate a JDBC connection to download all EOD history tables from POS client to its Staging DB. | Edward | Must Have | Carl | ESB-SAL-03
ESB-SAL-03-04 | POS Client EOD Data Process - Update Synchronization Status | Update data synchronization status in Staging database and POS client. | Edward | Must Have | Carl | ESB-SAL-03
ESB-SAL-03-05 | POS Client EOD Process Job Summary | The end of the job also log down the demanded information for user to collect details of data of the job running progress & result. | Edward | Must Have | Carl | ESB-SAL-03
ESB-SAL-04 | POS Client EOD Data Process - Data Processing to EDW | Send sales data to EDW Service Bus Staging DB for End of Day process (EOD) | Edward | Must Have | Polly
ESB-SAL-04-01 | POS Client EOD Data Process - Data Processing to EDW - DB-to-DB copy to EDW Staging Table | The EOD data will directly transfer the full data set to EDW. | Edward | Must Have | Polly | ESB-SAL-04
ESB-SAL-04-02 | POS Client EOD Data Process - Data Processing to EDW - Multiple Business Date Handling | Service bus EOD process will also need to distinct the data’s business date when copying the data from POS client to staging database. Because sometimes the POS client will accumulate multiple day’s data in one EOD process, the service bus EOD job shall identify this kind of data belonging to different business date. Hence, the process shall justify the raw data’s creation date against the cut-off time (4a.m.). | Edward | Must Have | Polly | ESB-SAL-04
ESB-SAL-04-03 | POS Client EOD Data Process - Data Processing to EDW - Validation Check | The service bus EOD processing job will validate the data with basic check sum logic upon total record count and total amount of target column | Edward | Must Have | Polly | ESB-SAL-04
ESB-SAL-04-04 | POS Client EOD Data Process - Data Processing to EDW - Exceptional Handling | EOD data process exception handling shall accumulate the exception data in a table and pending for operation team’s manual involvement. | Edward | Must Have | Polly | ESB-SAL-04
ESB-SAL-04-05 | POS Client EOD Data Process - Data Processing to EDW - Update Synchronization Status | Update data synchronization status in Staging database and POS client | Edward | Must Have | Polly | ESB-SAL-04
ESB-SAL-04-06 | POS Client EOD Data Process - Data Processing to EDW - Process Job Summary | The end of the job also log down the demanded information for user to collect details of data of the job running progress & result | Edward | Must Have | Polly | ESB-SAL-04
ESB-PRZ-REQ-01 | Pricing/Master Data Processing | Prepare price and master data before synchronization to POS client | Steven | Must Have | Wing
ESB-PRZ-REQ-01-01 | Pricing/Master Data Preparation | The service bus will trigger old stored procedure to trigger the pricing/master data preparation. | Steven | Must Have | Wing | ESB-PRZ-REQ-01
ESB-PRZ-REQ-01-02 | Pricing/Master Data Download to Staging | After the pricing data is prepared, the service bus shall run an application download the full set pricing/master data from pricing server to Staging DB. | Steven | Must Have | Wing | ESB-PRZ-REQ-01
ESB-PRZ-REQ-01-03 | Pricing/Master Data Pre-Distribution Process | Update data synchronization status in Staging database and POS client. | Steven | Must Have | Wing | ESB-PRZ-REQ-01
ESB-MST-REQ-02 | Pricing/Master Data Distribution | Distribute price and master data to POS client | Steven | Must Have | Carl
ESB-MST-REQ-02-01 | Pricing/Master Data Distribution - Initialization | The distribution process submitted by the job controller initiates a JDBC connection to update data into POS client. | Steven | Must Have | Carl | ESB-MST-REQ-02
ESB-MST-REQ-02-02 | Pricing/Master Data Distribution - Integrity Check | The process checks the total number of records to ensure the distribution is successful. | Steven | Must Have | Carl | ESB-MST-REQ-02-01
ESB-MST-REQ-02-03 | Pricing/Master Data Distribution - Incremental Update to POS Client | Data process will use incremental update towards POS clients. | Steven | Must Have | Carl | ESB-MST-REQ-02-02
ESB-MST-REQ-02-04 | Pricing/Master Data Distribution - Update Synchronization Status | Update data synchronization status in Staging database and POS client. | Steven | Must Have | Carl | ESB-MST-REQ-02-03
ESB-MST-REQ-02-05 | Pricing/Master Data Distribution - Process Job Summary | Job running summary will allow user to trace back the status and result of the schedule job. | Steven | Must Have | Carl | ESB-MST-REQ-02-04
ESB-NF-REQ-01 | Non-functional Requirements | Non-functional requirement | Steven | Must Have | Maxim's IT
ESB-NF-REQ-01-01 | System Dashboard View - Real Time | The system dashboard for real time sales data processing shall show the summary of every full batch of jobs covering all the POS clients, and contain a brief summary of it. | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-02 | POS Data Source Control - Control Indicators for Easy Manipulation | The POS data source will have control indicators which enables the jobs easily manipulate them. | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-03 | POS Data Source Control - Password Protected on Data Source Table | For privacy concern, the password preserved in the data source control table shall be encrypted by private key. | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-04 | System Exception Report - Jobs Process | The job process exception shall be collected and viewable by the user according to the exception’s severity. | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-05 | System Exception Report - Data Process | Before EOD process, if there’s still discrepant data accumulated in the exceptional data table, the system shall send out a data exception report to application support team. | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-06 | System Exception Handling - Jobs Process | Job processing retry mechanism - Real Time processing | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-07 | System Exception Handling - Data Process (EOD) | Job processing retry mechanism, will be introduced into several stages - EOD processing | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-08 | System Job Control - Polling Schema Maintenance | Polling schema maintenance will provide a UI for system admin to maintain the polling schema | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-09 | System Job Control - Branch Master Initiation | The data source data could be initialized into the system by migration from Maxim’s existing system called “Branch Master” | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-01-10 | System Configuration | Define system’s Configuration Items | Steven | Must Have | Maxim's IT | ESB-NF-REQ-01
ESB-NF-REQ-02 | System Interface | System Interface | Tommy | Must Have | Maxim's IT
ESB-NF-REQ-02-01 | Sales Data Web Service | Web Service Interface allow external application calls to post a complete sales order data to EOD. | Tommy | Must Have | Maxim's IT | ESB-NF-REQ-02
ESB-NF-REQ-02-02 | Pricing/Master Data DB Adapter | DB adapter to trigger the stored procedures to prepare pricing/master data. | Tommy | Must Have | Maxim's IT | ESB-NF-REQ-02
ESB-NF-REQ-02-03 | Sales Data DB Adapters - Total Number | DB adapters to query the total number of records being transferred in current EOD/real-time batch against the history tables. | Tommy | Must Have | Maxim's IT | ESB-NF-REQ-02
ESB-NF-REQ-02-04 | Sales Data DB Adapters - Total Amount | DB adapters to query the total amount of records being transferred in current EOD/real-time batch against the history tables. | Tommy | Must Have | Maxim's IT | ESB-NF-REQ-02
ESB-NF-REQ-02-05 | Pricing/Master Data DB Adapter | DB adapter to update/insert convert log into EDW. | Tommy | Must Have | Maxim's IT | ESB-NF-REQ-02

## Design Consideration
Design Consideration
NO. | Name | Remarks | Design Consideration
1 | Log Growing Consideration | Each date 1M of records created. | SQL Compression Mode / Bulk Copy /
2 | Performance Consideration
3 | Latency
4 | Overhead (Size overhead) on keeping HISTORY for EDW synchronization
5 | Use parameter table to store cut off date