## Schedule
Maxims' POS Polling ESB Implementation Master Schedule | [21 empty] | Original Live Run | [5 empty] | New Live Run
No. | High Level Project Timeline |  | From | To | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05
1 | Project Initialization |  | 2016-11-07 | 2016-11-18
2 | User Requirement Confirmation |  | 2016-11-14 | 2016-12-23
3 | Hardware/VPN/Environment Setup |  | 2016-12-19 | 2017-01-13
4 | System Analysis and Design |  | 2016-12-19 | 2017-01-13
5 | System Development |  | 2017-01-09 | 2017-03-03
6 | System Test |  | 2017-02-20 | 2017-03-10
7 | System Integration Test |  | 2017-02-27 | 2017-03-17
8 | Training |  | 2017-03-13 | 2017-03-17
9 | User Acceptance Test |  | 2017-03-13 | 2017-03-31
10 | Operation Acceptance Test |  | 2017-03-27 | 2017-04-07
11 | Capacity, Performance and Penetration Test |  | 2017-04-03 | 2017-04-13
12 | Deployment |  | 2017-04-21 | 2017-04-21
13 | Post Implementation |  | 2017-04-18 | 123/13
[11 empty] | Christmas's Holiday |  |  |  |  | CNY Holiday
Resources Calendar
Project Manager |  | Dick |  |  | 5 | 5 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [7 empty] | 49
Solution Architect |  | Steven |  |  |  | 3 | 3 | 2 |  | 4 | 4 |  | 4 | 4 | [21 empty] | 24
System Analyst 1 |  | Edward |  |  |  | 4 | 4 | 4 |  | 4 | 5 |  | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2.6 | 2 | 3 | 3 | [7 empty] | 75.6
System Analyst 2 |  | Steven / Tommy / Loan from DSAT |  |  |  | 4 | 4 | 4 |  | 4 | 5 |  | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.25 | [9 empty] | 81.25
Analyst Programmer 1 |  | Lotic |  |  |  | 1 | 1 | 1 |  |  | 5 |  | 3 | 4 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [7 empty] | 80
Analyst Programmer 2 |  | Parko |  |  |  | 1 | 1 | 1 |  |  | 5 |  | 3 | 4 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [8 empty] | 75
Tester1 |  | Tester 1 / Loan from DSAT | [16 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [10 empty] | 21
Tester 2 |  | Tester 2 / Loan from DSAT | [16 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | [9 empty] | 34
0 | [35 empty] | 439.85
4 weeks
6 weeks = 4 weeks +
2 weeks (Holidays)

## Task Break Down
|  | Total Project Sum |  | 446.85
# | Development Stage | Task Name | Details & Deliverables | Manday | By | From | To | Actual End | Status
1 | Project Management + Related Documentation | PMP Doc |  | 46 | Dick | 2016-11-07 | 2017-04-21
2 | Enviornment Setup | Prepare Development Environment |  | 20 | Steven | 2016-12-12 | 2016-12-12 | 2016-12-12
3.1 | System Analyst and Design | Impact analysis & the report |  | 40
3.2 | System Analyst and Design | System Design Document
3.3 | System Analyst and Design | Unit Test Plan
3.4 | System Analyst and Design | SIT Test Plan
| Development | Sum Total |  | 160.85 |  | 2016-12-19 | 2017-01-13
4 | Development | ZH Development Envrionment Setup |  | 3 | Benjamin | 2016-12-19 | 2016-12-21 | 2016-12-22
5 | Development | Technical Design Document
6 | Development | Staging Database setup |  |  | Lotic
7 | Development | Dummy POS Client DB Setup |  |  | Benjamin
8 | Development | Dummy EDW DB Setup |  |  | Benjamin
8.1 | Sub task | - Virtual Branch Staging Tables |  |  | Benjamin
8.2 | Sub task | - Others (Logs, Master related) |  |  | Benjamin
9 | Development | Dummy Pricing/Master DB Setup | 1.DB tables 2.Schema (*.sql file) |  | Parko
10 | Development | Framework/project structure building | Parent common api core web sql (please do create this source control project for DB schemas) | 3 | Parko | 2016-12-19 | 2016-12-22 | 2016-12-21
11 | Development | File encryption/decryption framework | Sources & Junits on: 1.File encryption 2.File decryption 3.Encryption failure handling 4.Decryption failure handling |  | Lotic
12 | Development | Values encryption/decryption framework (DB contained user/password focus) | Sources & Junits on: 1.Value encryption 2.Value decryption 3.Encryption failure handling 4.Decryption failure handling |  | Lotic
13 | Development | System parameter configuration |  |  | Lotic
13.1 | Sub task | - List all considered system parameters in excel |  |  | Lotic
13.2 | Sub task | - UI Mockup & Page Functional Design | 1.UI Mockup 2.Functional Design Document on the pages |  | Lotic
13.3 | Sub task | - Code & Unit Testing | Sources & Junits on: 1. CRUD 2. Parameter effective scenarios (affect related application process) |  | Lotic
14 | Development | Error handling framework development - Exceptions Design - Severity - Error Code - Error Message | List of System Error/Exception in excel including all details mentioned |  | Parko, Lotic
15 | Development | Job centralization controller |  |  | Parko
15.1 | Sub task | - Quartz Scheduler Spring Integration |  | 1 | Parko | 2016-12-22 | 2016-12-22 | 2016-12-22
15.2 | Sub task | - Quartz Schedulers (6 main controllers) |  |  | Parko
15.3 | Sub task | - Parent Job Control, Job Control Detail and Job Logs |  |  | Parko
15.4 | Sub task | - Junits
16 | Development | Sales data online polling jobs (POS - Staging)
16.1 | Sub task | - Single Polling Job with one poll scheme as parameter (Table to table) | 1.Copy tables to tables according to poll scheme 2.Check sum validation
16.2 | Sub task | - Child Job Control, Job Control Details & Job Logs (levarage task 17-21)
16.2 | Sub task | - Job Depenency Handling (levarage task 17-21)
16.3 | Sub task | - Polling job multi-threading consideration and implementation
16.4 | Sub task | - Junits
17 | Development | Sales data online pushing job (Staging - EDW)
| Sub task | - Single Polling Job with one poll scheme as parameter (Table to table) | 1.Poll scheme processing logic (active, time frame, DB conneciton, etc.) 2.Copy tables to tables according to poll scheme 3.Check sum validation
| Sub task | - Polling job multi-threading consideration and implementation | Multiples jobs triggered by quartz parent job and iterate all available poll scheme
| Sub task | - Junits
18 | Development | Sales data EOD polling jobs (POS - Staging)
| Sub task | - Single EOD Polling Job with one poll scheme as parameter (Table to table) | 1.Poll scheme processing logic (active, time frame, DB conneciton, etc.) 2.Copy tables to tables according to poll scheme 3.Check sum validation
| Sub task | - Polling job multi-threading consideration and implementation | Multiples jobs triggered by quartz parent job and iterate all available poll scheme
| Sub task | - Junits
19 | Development | Sales data EOD pushing jobs (Staging - EDW)
| Sub task | - Single EOD Polling Job with one poll scheme as parameter (Table to table) | 1.Poll scheme processing logic (active, time frame, DB conneciton, etc.) 2.Copy tables to tables according to poll scheme 3.Check sum validation
| Sub task | - Polling job multi-threading consideration and implementation
| Sub task | - Junits
20 | Development | Pricing/master data generattion job (Pricing Server - Staging)
21 | Development | Pricing/master data distribution jobs (Staging - POS)
| Sub task | - Single Pricing/Master Distribution Job with one poll scheme as parameter (Table to table) | 1.Poll scheme processing logic (active, time frame, DB conneciton, etc.) 2.Copy tables to tables according to poll scheme 3.Check sum validation
| Sub task | - Polling job multi-threading consideration and implementation
| Sub task | - Junits
22 | Development | Reporting
23 | Development | Alert Email
24 | Development | Backup & Housekeeping
25 | Development | SIT & UAT Envrionment Setup
26 | System Integration Test | Produce Integration Test Plan |  | 67 | To be Assigned | 2017-02-06 | 2017-02-24
27 | System Integration Test | Conduct Integration Test (EDW End-to-End - Sales Data Service)
28 | System Integration Test | Conduct Integration Test (Pricing & Master Data End-to-End Test)
29 | System Integration Test | Conduct Integration Test (Operational function and reporting testing)
30 | System Integration Test | Deploy to UAT environment
31 | IT Acceptance Test | Conduct IAT |  | 9 | To be Assigned | 2017-03-06 | 2017-03-24
32 | User Acceptance Test | Prepare UAT Plan (by Maxim) |  | 51 | To be Assigned | 2017-03-06 | 2017-03-24
33 | User Acceptance Test | Training Material (Operations, Administration and Reporting)
34 | User Acceptance Test | Conduct UAT Briefing and Training
35 | User Acceptance Test | Conduct Training Sessions (Technical, Operation and Business)
36 | User Acceptance Test | Conduct and Support UAT
37 | Performance and Penetration Test | Prepare performance test cases and scripts |  | 6 | To be Assigned | 2017-03-13 | 2017-03-24
38 | Performance and Penetration Test | Perform performance test |  | 16
39 | Operation Acceptance Test | Conduct OAT (including Resilience (HA) and Disaster recovery (DR) Test |  | 4 | To be Assigned | 2017-03-27 | 2017-04-07
40 | Implementation | Prepare Implementation Plan |  | 3 | To be Assigned | 2017-04-17 | 2017-04-21
41 | Implementation | Production Setup Implementation |  | 5
42 | Documentation | System Manual |  | 2 | To be Assigned | 2017-02-27 | 2017-03-03
43 | Post Implementation | Maintenance Transition |  | 10 | To be Assigned | 2017-04-17 | 2017-04-28
Formulas:
To = [From]+[Manday]
Note on E76: Edward Leung: Add one

## Deliverables Description
Maxim's ESB Implementation Project
Deliverables Description
Impact Analysis |  | Description | Deliverables
1 | IT51/52/53 data flows (the consideration of cut-over) | In-Scope Data Vs Out-Of-Scope Data | Impact Analysis Report
2 | Plan implementation strategy I | Cut-Over Procedure For In-Scope Data And The Impacts To Other Systems | Impact Analysis Report
3 | Plan implementation strategy II | The Alternation Of Out-Of-Scope Data And The Impacts To Other Systems | Impact Analysis Report
4 | Contingency | Any Work Around For Non-Changeable Items | Impact Analysis Report
5 | Work-Around Approach | - The Detail Work-Around Approach For Non Changeable Items | Impact Analysis Report
- Pros & Cons/Drawbacks
- Impacts To Maxim's IT
System Design |  | Description | Deliverables
1 | System Design Document - Architecture Design | Overall Architecture Diagrams And System Context | System Design Document
2 | System Design Document - Data Model Design | - Pos Client Data Source Data Model | System Design Document
- Dew Data Model
- Pricing/Master Data Model
- Staging Table Data Model (If Different From Above)
- Polling Application Work Tables
A) Job Control (Job Logs, Exceptional Data)
B) System Parameters
C) Pops Clients/Data Source Control
D) Reporting Data (Optional)
3 | System Design Document - High Level Interface Design | - Internal Interfaces Built By OSB | System Design Document
- External Interfaces Implemented by Layers
4 | System Design Document - Functional Design | - The Application Design Which Reflects Both Functional And Non-Functional Requirements | System Design Document
- Application Mock-Up Screens
5 | System Design Document - Report Design | - Report Logic | System Design Document
- Report Layout
- Output Format
- Error/Exceptions
6 | System Design Document - Interface Specification | - Detail Interface Specification | System Design Document
A) Interface Types
B) Data Process Flow
C) Other: Direction, Logging, Error Code
B) Field Mapping Table
7 | Technical Design Document - Infrastructure | - Configuration | Technical Design Document
- Technologies
- Infrastructure And Environments
- System Management & Monitoring
8 | Technical Design Document - Interface Clients Management | - Inbound/Outbound Rules Between Pops Clients & Maxim HQ Data | Technical Design Document
- POS Clients Data Source Management
A) MS SQL Server 2000
B) DBF File (MySQL)
C) CSV File
9 | Technical Design Document - UI Application Program Flows | - System Context | Technical Design Document
- Logic Flows
- Component & Module Design
10 | Technical Design Document - Data Flows | - Data Flow Diagram | Technical Design Document
- Data Loading Logic
- Table Field Mapping
- Logs, Exceptions
11 | Technical Design Document - Data Model | - Data Model | Technical Design Document
- View, Indexes & Constraints
- Stored Procedures & Triggers
12 | Technical Design Document - Jobs | - Job Scheduler Frameworks | Technical Design Document
- Job Control & Management (Trigger, Re-Run, Failure Handling And Monitoring)
- Thread Control Model (Thread Pool Size, Run-Management)
13 | Technical Design Document - Job Details | - Job Processing Flow | Technical Design Document
- Job Life Cycle (Creation, Config, Re-Run, Abort)
- Job Handling (Monitor, Pause, Resume)
- Logs & Exceptions
14 | Technical Design Document - Backup & Housekeeping | System Data Backup & Housekeeping | Technical Design Document
System Testing (Unit Test / SIT / UAT) |  | Description | Deliverables
1 | Unit Testing Document | - Test Cases, Expected Test Results | Unit Test Plan, Unit Test Results
- Testers, Test Dates, Test Results
2 | SIT Testing Document | - SIT Schedule, SIT Testing Environment, SIT Communication Planning, SIT Issue Log | SIT Test Plan, SIT Test Results
- SIT Test Scenario, SIT Cases, Expected Test Result
- Testers, Test Dates, Test Results
3 | UAT Testing Document | - UAT Schedule, UAT Testing Environment, UAT Communication Planning, UAT Issue Log | UAT Test Plan, UAT Test Results
- Testers, Test Dates, Test Results
Implementation |  | Description | Deliverables
1 | Implementation Document | - Milestones and Target Dates | Implementation Plan
- Pre-requisite of Object Distribution / System Installation
- Data Initiation
- Verification
- Fall Back Plan
2 | User Manual | - User operation guide for POS end users | User Manual
- EOD Procedures
- Other Related User Operation Guide
3 | Operation Manual | - Administrator Operation Guide | Operation Manual
- Parameter Setup
- POS Site Setup
4 | System Installation Guide | -Oracle DB XE 11.2 | System Installation Guide
-JDK 1.8_101
-XMing and related Linux64 components (support package for SSH UI of Oracle Universal)
-WebLogic 12c
-SOA & Enterprise Manager
-OSB 12c