## Sheet1
Major Task: Installation and Configuration of OSB
Item |  | Description | Details (on SVN) | Last completed by | Last Update | Completed | Status
1 |  | Install SOA Suite 12c & OSB | //192.168.0.0/download/oracle_soa_12.1.6.jar | Tommy | 2017-03-30 | Yes
| 1.01 | land to the UAT linux | installation guide : //192.168.0.0/landToUAT.docx | Tommy | 2017-03-01 | Yes
| 1.02 | Executable Software Ready | same as 1.1 | Tommy | 2017-03-30 | Yes
| 1.03 | Setup install user and path | same as 1.1 | Tommy | 2017-03-30 | Yes
| 1.04 | Create Oracle / Applicaton Directory |  | Tommy | 2017-03-30 | Yes
| 1.05 | Install Linux Patch |  | Tommy | 2017-03-30 | Yes
| 1.06 | Install X Window for Oracle Setup (Window) |  | Tommy | 2017-03-30 | Yes
| 1.07 | Config Connection to X Window in Linux |  | Tommy | 2017-03-30 | Yes
| 1.08 | Config Host / Nameserver in Linux |  | Tommy | 2017-03-30 | Yes
| 1.09 | Install SOA & OSB software |  | Tommy | 2017-03-30 | Yes
| 1.1 | Create SOA Repostory |  | Tommy | 2017-03-30 | Yes
| 1.11 | Create and Config domain for SOA (Cluster Setup) |  | Tommy | 2017-03-30 | Yes
| 1.12 | Repeat Step 1.3 to 1.9 in secondary |  | Tommy | 2017-03-30 | Yes
| 1.13 | Replicate SOA Domain Template from UAT 1 -> UAT2 |  | Tommy | 2017-03-30 | Yes
| 1.14 | Upload the Prepared Start / Stop / Deploy Script |  | Tommy | 2017-03-30 | Yes
| 1.15 | Start the nodemgr / Amin |  | Tommy | 2017-03-30 | Yes
| 1.16 | Login to Admin Console |  | Tommy | 2017-03-30 | Yes
| 1.17 | Start / Stop the soa/osb Server and verify the cluster work |  | Tommy | 2017-03-30 | Yes
| 1.18 | Login to UAT SOA Suite |  | Tommy | 2017-03-30 | Yes
| 1.19 | Increase Process Count |  | Tommy | 2017-04-20 | Yes
| 1.2 | Update Name Server |  | Tommy | 2017-04-20 | Yes
2 |  | Install Applications | //192.168.0.0/download/oracle_soa_12.1.6.jar | Tommy | 2017-03-30 | Yes
| 2.01 | Create and Config domain for Application (Cluster Setup) |  | Tommy | 2017-03-30 | Yes
| 2.02 | Replicate Applicartion Domain Template from UAT 1 -> UAT2 |  | Tommy | 2017-03-30 | Yes
| 2.03 | JDBC connection |  | Tommy | 2017-03-30 | Yes
| 2.04 | Upload the Prepared Start / Stop / Deploy Script |  | Tommy | 2017-03-30 | Yes
| 2.05 | Start the nodemgr / Amin |  | Tommy | 2017-03-30 | Yes
| 2.06 | Login to Admin Console |  | Tommy | 2017-03-30 | Yes
| 2.07 | Start app Server and verified the cluster work |  | Tommy | 2017-03-30 | Yes
| 2.08 | JDBC connection | JDBC configuration guide : //192.168.0.0/uat_jdbc_con.docx | Tommy | 2017-03-30 | Yes
| 2.09 | Deploy the stg application / edw application |  | Tommy | 2017-03-30 | Yes
| 2.1 | Setup Staging Database |  | Tommy | 2017-03-30 | Yes
| 2.11 | Setup of EDW Application |  | Tommy | 2017-04-07 | Yes
| 2.12 | Proxy Setup for Maxim Pos Application |  | Tommy | 2017-04-07 | Yes
| 2.13 | Proxy Setup for Maxim EDW Application |  | Tommy | 2017-04-07 | Yes
| 2.14 | Mount Window Share Drive |  | Tommy | 2017-04-10 | Yes
3 |  | Deployment and OSS Config | //192.168.0.0/download/oracle_osb_12.1.5.jar
| 3.01 | Login to UAT SOA Suite | installation guide : //192.168.0.0/landToUAT.docx | Tommy | 2017-03-01 | Yes
| 3.02 | Config the Routing in Development |  | Lotic | 2017-04-10 | Yes | COMP
| 3.03 | Deploy Configuration to SIT |  | Tommy / Lotic | 2017-04-11 | Yes | COMP
| 3.04 | Update Application to Point to OSB |  | Tommy | 2017-04-11 | Yes | COMP
| 3.05 | Test the routing |  | Tommy | 2017-04-11 | Yes | COMP
| 3.06 | Setup UAT SOA Cluster |  | Tommy | 2017-04-12 | YES | COMP
| 3.07 | Deploy and Config ESB UAT |  | Tommy | 2017-04-12 | YES | COMP
| 3.08 | Test the routing in UAT |  | Tommy | 2017-04-12 | YES | COMP
4 |  | Funcationality
| 3.01 | Real Time From POS to Staging (POSSQL) |  | Tommy | 2017-04-11 | Yes
| 3.02 | Real Time From Staging to EDW (POSSQL) |  | Tommy | 2017-04-06 | Yes
| 3.01 | Real Time From POS to Staging (POSSQL) -Configuration |  | Edward | 2017-04-06 | Yes
| 3.02 | Real Time From Staging to EDW (POSSQL) -Configuration |  | Edward | 2017-04-06 | Yes
| 3.05 | Real Time From POS to Staging (DBF) |  | Tommy | 2017-04-06 | No
| 3.06 | Real Time From Staging to EDW (DBF) |  | Tommy | 2017-04-06 | No
| 3.09 | Real Time From POS to Staging (DBF) - Configuration |  | Edward |  | No
| 3.1 | Real Time From Staging to EDW (DBF) -Configuration |  | Edward |  | No
| 3.07 | Real Time WebService |  | Tommy | 2017-04-06 | Yes
| 0.01 | EOD From POS to Staging (POSSQL) - Configuration |  | Tommy | 2017-04-06 | Yes
| 0.02 | EOD From Staging to EDW (POSSQL) - Configuration |  | Tommy | 2017-04-06 | Yes
| 3.03 | EOD From POS to Staging (POSSQL) |  | Tommy | 2017-04-06 | Yes
| 3.04 | EOD From Staging to EDW (POSSQL) |  | Tommy | 2017-04-06 | Yes
| 3.1 | EOD From POS to Staging (DBF)- Configuration |  | Edward |  | No
| 3.11 | EOD From Staging to EDW (DBF)- Configuration |  | Edward |  | No
| 3.08 | EOD From POS to Staging (DBF) |  | Tommy | 2017-04-06 | Yes
| 3.09 | EOD From Staging to EDW (DBF) |  | Tommy | 2017-04-06 | Yes
| 3.1 | EDW Convert Log |  | Tommy | 2017-04-06 | Yes
| 3.11 | Master From Pricing to Staging (POSSQL)- Configuration |  | Edward |  | No | WIP | confim some missing table is POS
| 3.12 | Master From Staging to POS (POSSQL)- Configuration |  | Edward |  | No | WIP | confim some missing table is POS
| 3.13 | Master From Pricing to Staging (POSSQL) |  | Lotic -> Tommy | 2017-04-06 | No | Testing
| 3.14 | Master From Staging to POS (POSSQL) |  | Lotic -> Tommy | 2017-04-06 | No | Testing
| 3.11 | Master From Pricing to Staging (DBF)- Configuration |  | Edward |  | No
| 3.12 | Master From Staging to POS (DBF)- Configuration |  | Edward |  | No
| 3.13 | Master From Pricing to Staging (DBF) |  | Lotic -> Tommy |  | No | Cancel
| 3.14 | Master From Staging to POS (DBF) |  | Lotic -> Tommy |  | No | Cancel
| 3.15 | Day End Report |  | Tommy | 2017-04-06 | Yes
| 3.16 | Email Alert |  | Joy | 2017-04-11 | Yes | COMP
| 3.17 | File Copy |  | Joy |  | No | WIP
| 3.18 | OSB Configuration |  | Lotic | 2017-04-11 | Yes | COMP
| 3.19 | Update JDBC Cconfigiration Method |  | Tommy | 2017-04-10 | Yes | COMP
| 3.2 | Real Time From POS to Staging (CSV) |  | Tommy |  | No | Dev Comp
| 3.21 | Real Time From Staging to EDW (CSV) |  |  |  | No | Dev Comp
| 3.22 | EOD From POS to Staging (CSV) |  |  |  | No | Dev Comp
| 3.23 | EOD From Staging to EDW (CSV) |  |  |  | No | Dev Comp
| 3.24 | Master From Pricing to Staging (CSV) |  |  |  | No | Cancel
| 3.25 | Master From Staging to POS (CSV) |  |  |  | No | Cancel
| 3.26 | Pos Different Schema |  |  |  | No | NIL | CR
| 3.27 | Master CSV / DBF Combine Output |  |  |  | No | Cancel | CR
| 3.28 | Branch Info Maint |  |  |  |  | Dev Comp
| 3.29 | Schema Info Maint |  |  |  |  | Dev Comp
| 3.3 | Branch Rerun |  |  |  |  | Dev Comp
| 3.31 | Password Encrytion |  | Tommy |  | COMP | Dev Comp
| 3.32 | Support Access Window Share Drive |  |  | 2017-04-10 | COMP
| 3.33 | Octopus Black List Requirement |  | Tommy | 2017-04-12 | COMP
| 3.34 | Octopus Black List |  | Joy
| 3.35 | Adavane Task Locking for Cluster |  | Tommy | 2017-04-12 | COMP
| 3.36 | Update Web Service
| 3.37 | Update Connection Issue |  | Tommy | 2017-04-21 | COMP
| 3.38 | Update User Process Issue |  | Tommy | 2017-04-20 | COMP
| 3.39 | Enhance Config |  | Tommy | 2017-04-25
| 3.4 | Update new Real Time Table
| 3.41 | update PK
4 |  | UAT Support
|  | Fix for DBF Copy |  |  | 2017-04-11 | COMP
5 |  | Production Preparation
|  | Stress Test 1 - 50 Branch |  | Tommy | 2017-04-26 | COMP
|  | Stress Test 2 - 300 Branch |  | Tommy | 2017-05-04 | COMP
Stress Test 2 - Muti POS