## Log
CG Support Log
# | Date | Name | Related Program / Module | Reason / Follow Up | Type | Owner | Supervisor | Status | Knowledge Base # | Deployment to Production Date
1 | 2017-01-16 | Files could not process. | Notification Source File Processing | Incorrect Field Mapping setup by users making it not able to process the file. | Configuration | Lotic | Edward | Closed | KB001 | 2017-01-17
2 | 2017-01-16 | In Notification Approval screen, Policy No & Claim No. display as empty for some touchpoints | Notification Source File Processing | UAT normal but production has problem. | Bug | Parko | Steven | Closed |  | 2017-01-17
3 | 2017-01-16 | In Notification Approval screen, add column "Touchpoint Status" after "Approval Status". | Notification Approval | Raymond request add one more column related to Touchpoint Status （Active/Inactive） So as to let users know whether the related message can send out or not during message fire process. | AXA Request | Parko | Steven | Closed |  | 2017-01-17
4 | 2017-01-16 | Notification not allowed to reject. | Notification Approval | For status equal to insufficient Info stop the users to carry reject Changes ：Apart from status equal to FAIL, SUCCESSFUL, OBSOLETE, notification allowed to reject | AXA Request | Parko | Steven | Closed |  | 2017-01-17
5 | 2017-01-16 | Event not triggered event in non effective date | Event | Logic related to the check need to fix. | Bug | Benjamin | Lotic | Closed |  | 2017-01-17
6 | 2017-01-16 | Non-Admin user click search button with select any touchpoint or sub business line, it will display the same business line but other sub business line content . | Notification Approval | System don't have related logic to check sub business line users searching criteria. | Bug | Lotic | Edward | Closed |  | 2017-01-17
7 | 2017-01-19 | System cannot decrypt file and put to error folder. Error message - decrypt file [D:\repos\cg\input\NotificationSource\core\source\ZEPIPI0034.pgp] fail, file [D:\repos\cg\input\NotificationSource\core\source\ZEPIPI0034.txt] not found | Notification Source File Processing | AXA has encryption file add un-expected PGP signature making CG not able to decrypt | AXA Bug | Lotic | Edward | Closed | KB001
8 | 2017-01-16 | Mark NB, POS, Renewal of individual health messages to rejected. Inactive those touchpoints | n/a | Per request by users Remarks: 'HTH0001, HTH0002, HTH0004' | AXA Request | Lotic | Edward | Closed
9 | 2017-01-16 | Mark NB, POS, Renewal of individual health messages to rejected. Inactive those touchpoints on Transaction date equal to YYYYMMDD | n/a | Per request by users Remarks: 'LIF0002', 'LIF0003' | AXA Request | Lotic | Edward | Closed
10 | 2017-01-19 | Incorrect Masking | Notification Message Sending | Data Masking should apply 'x' to the 5th to 9th digit in display fields. However, program , now 5 to 8 | Bug | Parko | Lotic | Closed |  | 2017-01-23
11 | 2017-01-19 | Ad-hoc requested by AXA to stop the sending of LIF0002, LIF0003 for the transaction date of 2017-01-18. | n/a | Core system provide incorrect LIF0002 (POS - Processing / POS - Complete) to customer. One of the AXA customer is the policy owner and noticed that it was an error. On 17:55 called us to stop the system. The system team paused the system and completed the suspend and resume on 20:00. | AXA Request | Lotic | Edward | Closed
12 | 2017-01-20 | Mark LIF0002, LIF0003 on the transaction date of 2017-01-19 to REJECTED | n/a | Same as #11 | AXA Request | Lotic | Edward | Closed
13 | 2017-01-23 | Files not found in CG. Lots of files not downloaded to CG. Only three of them | Hardware / System Related Issue | Investigation in progress. ESG has file sent to SFTP server. But no files and log files shows there were records downloaded. | Network | Edward | n/a | Open | KB001
14 | 2017-01-23 | Policy number starts with '0' cannot map to correct hotline number |  | Checking programming logic | Bug | Linwood | Lotic | Closed | KB002 | 2017-02-02
15 | 2017-01-23 | Set grouping in touchpoint by Policy Number. However user expect it can group by cert number. The grouping make incorrect grouping | Notification Message Sending | Determine cost and time to allow grouping by Certificate number | AXA Request | Edward | n/a | Open | KB002
16 | 2017-01-23 | Numeric file claim amount format is 0000000000000500 equal to 5.00. User asked when we can carry out conversion on number. | Notification Message Sending | Need to change program to add "is numeric" in field mapping configuration screen. | AXA Request | Edward | n/a | Open | KB002
17 | 2017-02-01 | User cannot log in and file in hotline folder cannot process | Database Issue | Database log full. Add back log file size. Pending: Add backup logic | Infrastructure | Billy | Edward | Closed | KB004
18 | 2017-02-01 | NHR (172.29.52.31 / 172.29.52.34) were down. | Hardware / System Related Issue | Issue fixed after ATOS MS team restart | Infrastructure | Albert | Edward | Closed | KB003
19 | 2017-02-01 | Policy number '10288801GH' cannot map to correct hotline number | Notification Message Sending | User provide policy number in mapping table is: '102888' but correct mapping policy number should be '10288801GH' | User Requirement | Jamie / Fiona | Edward | Closed

## Task List to ATOS
Task List to ATOS
# | Name | Related Support Log # | Status | AXA Staff | Party | By | Priority | Start | End
T1 | Confirm VM Backup or DB Backup on Prd / UAT database |  | Not Start |  | Buzz IT | Billy | High | 2017-02-09 | 2017-02-10
T2 | CR for Log #15. Allow grouping of cert number in message | 15 | CR quotation submitted | Jamie | ATOS | ??? | High | 2017-02-07 | 2017-04-03
T3 | CR for Log #16. Allow handling of claim amount field (number / 100) | 16 | CR quotation submitted | Shawn | ATOS | ??? | High | 2017-02-07 | 2017-04-03
T4 | CR : Web API Amendment: Display message type name (e.g. New Business / POS Claim ..) according to the newly added language parameter in NHR web interface. |  | CR quotation submitted |  | ATOS | ?? | High | 2017-02-07 | 2017-04-03
T5 | CR: Web API Amendment: Group Delivery Status to Successful and Not-Successful in Web Service call for iPro/SCRUM inquiry |  | CR quotation submitted |  | ATOS | ?? | High | 2017-02-07 | 2017-04-03
T6 | CR: Notification History Inquiry: Allow the searching of NHR record by Recipient's Phone Number (SMS) and Recipient's Email Address (Email) |  | CR quotation submitted |  | ATOS | ?? | High | 2017-02-07 | 2017-04-03
T7 | ICF web service live run |  | Support UAT / Delay due to AXA internal Party Issue | CHARLEUX Bruno <bruno.charleux@axa-groupsolutions.com> | Buzz IT | Steven Chen | High | 2016-12-01 | 2017-01-31
T8 | NHR move back to AXA |  | Start Discussion | Steven Guo | Buzz IT | Edward | Medium | 2017-02-01 | 2017-03-31
T9 | 17 Security Issues Fixing |  | Not Start | Steven Guo | Buzz IT | Steven Chen | Low
T10 | Investigate why NHR was down on 01-Feb-2017 | 18 | Pending | Steven Guo | Buzz IT | Edward | Low | 2017-02-08 | 2017-02-28
T11 | Load Balancing IP / Purchase Hardware Loan Balancer ??? |  | Pending |  | ATOS |  | Low
T12 | Activation of Windows License |  | Pending |  | ATOS |  | Low
T13 | Purchase of sftp Server |  | Pending |  | Buzz IT | Edward | Low
T14 | Purchase of QuartzDesk License |  | Pending |  | Buzz IT | Edward | Low
T15 | Submission of Technical Specification |  | Pending |  | Buzz IT | Steven Chen | Low
T16 | Monitoring List (CPU, Memory, Disk, Space) |  | Pending |  | Buzz IT | Edward | Low
T17 | Provide Reboot Sequence |  | Pending |  | Buzz IT | Edward | Low

## Knowledge Base
CG Knowledge Base
Knowledge Base # | Knowledge Description | Shared By | Publish Date | Updated By | Last Update Date
KB#001 | No core file downloaded to CG | Edward | 2017-02-14
KB#002 | Invalid Notification Content | Edward | 2017-02-14
KB#003 | Notification History Reposition is Download | Edward | 2017-02-14
KB#004 | CG cannot login | Edward | 2017-02-14

## KB001
Knowledge Base | No core file downloaded to CG
Knowledge Base No. | KB001
Related Email | N/A
Support Procedure | 1. Call Amy, Edward or Wayne to see whether they receive alert email or not ?
2. If they have email recevied, forward the email to AXA Level One support. The message is asking their core systems to follow up.
3. If they don't have email receivied, it is possible that all records are rejected or there is no file content in the core file.
4. To check, login to CG
5. Go to related business line (e.g. Life, Group Health, etc) 6. Go to Notification Management > Notifiation Source Upload 7. Select Transaction Date and check whether there are touchpoints for the date
8. If total number of records is zero. Contact core system team. Mentioned that for this touchpoint, there is no record in the file.
9. If all records are error, use Winscp to login to /cygdrive/d/repos/cg/input/NotificationSource/core/error (host: 43.248.166.73 / user id: axa-sys / password: P@ssw0rd )
10. Check on the current date or yesterday, whether there are error file found.
11. Download the file and check the error content. Send to relatd core system team for follow up.
Appendix | Daily Download File
Core Files Downloaded
|  | Business Line | System | Interface File Prefix | TouchPoint | Download Time | Destination Folder
|  | Life | RLS | RSNB |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Life | RLS | RSPP |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Life | RLS | RSPC |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Group Health | EB | GPPNDCLM |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZENBNB |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZEPCPC |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZERCRC |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZEPIPI |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZEPGPG |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZECICI |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Individual Health | G400 | ZECGCG |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | CLAP |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | CLSB |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | ENIS |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | ENSB |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | NBIS |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | RNWI |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | P&C | PSEA | RTNM |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
|  | Channel (RCMS) | RCMS | RCMS |  | To be confirmed | /cygdrive/d/repos/cg/input/NotificationSource/core/source
Notification Date
Touchpoint
If Total No. of Records is zero.
Input Date
Click Search

## KB002
Knowledge Base | Invalid Notification Content
Knowledge Base No. | KB002
Related Email | N/A
Support Procedure | 1. Ask user to send us the related email / SMS
2. Ask user to provide what is the related business line and touchpoint
3. Go to CG, notification approval screen. See whether you can get the record. (Too old record might not be able to found. CG only keep records for a few years of record!)
4. Select the content and click View
5. If the content is incorrect per definition defined by end users. Report this to application team.
6. If the content is correct, please also go to Report > Notification History Inquiry.
Input criteria
Click both choices
After input
criteria, click Search
Source file content
Content

## KB003
Knowledge Base | Notification History Repository is down
Knowledge Base No. | KB003
Related Email | N/A
Support Procedure | 1. Go to CG, go to Report > Notification History Inquiry
2. If there is bank page, it means the web servcies of NHR not working.
3. If it has blank screen as follows. NHR connection is not working
4. Open the browser, type in the URL as follows:
https://nhr.e-service-axa.com.hk/axa-nhr-web/spring/nhr/getNotificationHistoryByXml
If you can see XML error, it means it has response. Contact application team
5. If there is no reply from the web service. Contact Infrastructure team for follow up.
Possible problem: NHR is not up. Proxy server not routing related http services.
6. If there is reply from the web service saying connection refused. Contact application team. The httpd service may down.
Go to this screen
It shows notification history but the screen is blank

## KB004
Knowledge Base | eNotification Portal Not Accessable
Knowledge Base No. | KB004
Related Email | N/A
Support Procedure | 1. Check user login to AXA internal network or not. There is whitelist set. For others, they cannot login. | Whitle List
| 2. If it is in the whitelist. Login to CG production Server. Please refer to server log. | Production Server List
3. Login to VPN of ATOS. Check Jboss is running or not
4. Check jboss is running
5. Login to http://172.29.52.24:9990/console/App.html
6. Check the service (master / slave) is running
7. If they are running, get all log files and send to application team for follow up.

## White LIst
White List
IP Address / Range | Party
125.215.144.6 | Range of AXA
118.140.97.218 | Range of Buzz IT
14.136.149.125 | Amar
125.215.144.6 | Synegery
183.31.235.74 | ZH Team
116.49.88.173 | Edward's Home
171.18.48.58 | SiteMinder
14.136.149.125 | Proxy Server of AXA HK
171.18.48.3 | AXA Tech Guangzhou
103.6.153.130 | Atos Office
122.152.142.91

## Production Server List
Production Server List - CG
Host Name | Host Usage | IP Address | User ID / Password
HKWVAPAXA01 | Active Directory Domain server / SQL Witness Server | 172.29.50.21 | PRD\Administrator / P@ssword1234
HKWVASAXA01 | Active Directory Domain server / SQL Witness Server (DR) | 172.29.52.25 | PRD\Administrator / P@ssword1234
HKWVAPAXA02 | Application Proxy server | 172.29.42.22 | PRD\Administrator / P@ssword1234
HKWVASAXA02 | Application Proxy server (DR) | 172.29.42.26 | PRD\Administrator / P@ssword1234
HKWVAPAXA04 | Application server | 172.29.52.24 | PRD\Administrator / P@ssword1234
HKWVASAXA04 | Application server/Communication Gateway (HA) (DR) | 172.29.52.28 | PRD\Administrator / P@ssword1234
HKWVAPAXA03 | Database server / Communication Gateway | 172.29.52.23 | PRD\Administrator / P@ssword1234
HKWVASAXA03 | Database server/Communication Gateway(DR) | 172.29.52.27 | PRD\Administrator / P@ssword1234
Production Server List - NHR
Host Name | Host Usage | IP Address | User ID / Password
HKLVAUAXA01A | Active Directory Domain server / SQL Witness Server | 172.29.52.29 | NHR\Administrator / P@ssword1234
HKLVAUAXA01B | Active Directory Domain server / SQL Witness Server (DR) | 172.29.52.32 | NHR\Administrator / P@ssword1234
HKLVAUAXA02A | Application Proxy server | 172.29.42.27 | NHR\Administrator / P@ssword1234
HKLVAUAXA02B | Application Proxy server (DR) | 172.29.42.28 | NHR\Administrator / P@ssword1234
HKLVAUAXA04A | Application server Communication Gateway (HA) | 172.29.52.31 | NHR\Administrator / P@ssword1234
HKLVAUAXA04B | Application server/Communication Gateway (HA) (DR) | 172.29.52.34 | NHR\Administrator / P@ssword1234
HKLVAUAXA03A | Database server Communication Gateway | 172.29.52.30 | NHR\Administrator / P@ssword1234
HKLVAUAXA03B | Database server/Communication Gateway(DR) | 172.29.52.33 | NHR\Administrator / P@ssword1234