## Breakdown
Man day Breakdown
Task | Team Lead | System Analyst | SA | Analyst Programmer | Analyst Programmer | SA Onshore |  | Analyst Programmer | Deliverable | Remarks
Project Management
Meeting and communication | 25 | [8 empty] | For coordinate with Infrastructure vendor, coordinate with business teams for UAT and prototype approval, coordinate with IT security for security test, coordinate with capacity team for load test, coordinate with external network vendor to setup new VPN.
Prepare PMP | 5 | [7 empty] | 1) Project Management Plan (D) 2) High Level Project Schedule (D)(T) | Review project / contract scope, includes draft and revision.
Progress Monitoring and Control | 10 | [7 empty] | 7) Issue Log (D) (T) 8) Risk Log (D) (T) 10) Project Status Summary (D)(T) 11) Change Request Form (D) (T) 12) Change Request Log (D) (T)
Post Implementation Review / Report; Maintenance Transition | 5
Other PM related documentation | 5 | [7 empty] | 3) Process Usage Plan (D)(T) 4) Configuration Management Plan (CMP) (D)(T) 5) Configurable Item Register (CIR) (D)(T) 6) Physical & Functional CM Audit Checklist (D)(T) 9) Quality Dashboard (D)(T)
Environment Setup
Prepare Development Environment |  | 4 | 5 |  | 5 |  |  |  | Dev environment (Vendor) | VM x 2 (1 x MD) on-shore VM x 2 (1 x MD) off-shore
Basic Testing MQ / Queue / Cluster Setup |  | 3 | 2.5 |  | 5
Basic Environment Testing |  | 2 | 2.5 |  | 5
System Analysis and Design
Application information Inquire |  | 15 | 15
Migration Planning (Change Analysis) |  | 15 | 10 |  | 5 | [5 empty] | Assume the list of application is ready
Migration Planning (Review Potential Compatibility Issues within MQSeries with Solution) |  | 12.5 | 10
Migration Planning (Review Potential Compatibility Issues General Spotting) |  | 15 | 15
Review & Confirm Post-upgrade Change & Requirement |  | 5 | 5
Review and Confirm Change & Requirements |  | 3 | 2.5
Produce System Design Specification |  | 5 | 5 | [5 empty] | 13) System Design Specification (SDS) (D)(T)
Produce Detail Migration Plan |  | 5 | 5 | [5 empty] | 14) Migration Plan (MP) (D)(T)
Review & Confirm Detail Migration Plan |  | 5 | 5
Produce Unit Test Plan |  | 3 | 0 |  | 5 |  |  |  | 16) Unit Test Plan (D)(T)
Review Unit Test Plan |  | 2 | 2.5
Migration Implementation
Produce Technical Design Specification |  | 6 | 5 |  | 5 |  |  |  | 15) Technical Specification (TS) (D)(T) - Environment Configure 23) System Document(D) (T) - Environment Configure
Implement Queue Manager Clustering | [8 empty] | Implement MQ Configuration in SIT environment | Implement MQ Configuration in SIT environment
Implement Queues - Remote/Alias & Unit Testing |  | 8 | 5 |  | 15 |  |  |  |  | Extra effort shall be needed for the coordination with 3rd Party Queue Manager owners 4 Queue Managers 14 Queue Manager Connections (2 Remote Cluster/MD to rebuild, 0.5 for SA to QA & verify the on-shore environment) 236 Remote Queues (10 Queues/MD to setup including communication, 0.3 for SA to QA and Follow up)
Implement Local Queue/Channel Configuration - Downline Application (DEV) | [9 empty] | 396 Local Queues 10-15 Queus/Day to Setup (0.3 for SA to QA and Follow up) 1 day/week for architect to QA work
Implement Local Queue/Channel Configuration - SITA Network (DEV) |  | 14 | 10 |  | 30
Channel Connectivity Test & Unit Test |  | 12 | 10 |  | 20 |  |  |  |  | 236 Channels Est 10-15 Channels/Day (0.5 for SA to QA and Follow up) | Write script / program to test
Deploy to SIT environment |  | 5 | 5 |  | 10
System Integration Test (MQ Series as Black Box)
Produce Integration Test Plan & Acceptance Criteria with Users |  | 5 | 5 |  | 10 |  |  |  | 17) System & Integration Test Plan (D)(T)
Conduct System Integration Test (Driven by CorpMQ Message Sender & Receiver) upon Sample Cases below - Client Connection Type - Local/Remote QM - Communication Pattern - Sender & Receiver |  | 36 | 25 |  | 50
Deploy to UAT environment |  | 10 | 10 |  | 5
IT Acceptance Test
Define Acceptance Criteria |  | 1 | 1 |  | 2 |  |  |  |  | Conduct with Middleware Team (1 session only).
Support Acceptance Test |  | 1 | 1 |  | 2 |  |  |  |  | Conduct with Middleware Team (1 session only).
User Acceptance Test Support (End-to-End) | [8 empty] | UAT refers to the end-to-end regression testing which starts from user/operation. This test may not be performed by user but CX IT or Testing Team to conduct an automated test upon full regression cases of in scope interfaces
Define Acceptance Criteria |  | 2 | 2 |  | 2 |  |  |  |  | Conduct with Middleware Team (1 session only).
Prepare UAT Plan | [8 empty] | 20) UAT Test Plan (D) (T)
Review UAT Plan |  | 3 | 3
Training Material (Operations, Administration & Housekeeping) |  | 4 | 4 | [5 empty] | 24) Training Document (D) (T) | Assuming leveraging User Manual's content to produce the training material
Conduct UAT Briefing &Training (Technical highlights, Testing Approach) |  | 3 | 3 | [6 empty] | Provides training to internal & external application teams in terms of the application technical highlights, and Testing Approach & Cycles.Assume THREE session for all relevant parties. 0.5 day for one session, and 0.5 of preparation 1 x 3 = 3 MD
Conduct and Support UAT (Driven by End Users) |  | 88.5 | 50 | [5 empty] | 21) UAT Defect Log (D) (T) 22) UAT Acceptance Form (D)(T)
Prepare Operational Manual |  | 1 | 1 |  | 3 |  |  |  | 25) Operational Manual (D)
Prepare Administration Guides (Installation and Configuration) |  | 2 | 2 |  | 2
Performance and Penetration Test (MQSeries as Black Box)
Prepare performance test cases and scripts |  | 2 | 2.5 |  | 5
Perform performance test |  | 4.5 | 5 |  | 5 |  |  |  | 19) System Performance Report (D)(T)
Full Regression Test | [9 empty] | (Assume: With Testing Script Provided)
Conduct the Regresion Test | [9 empty] | Appx 130 Application
Code Change
Devolopment |  | 0 | 10 |  | 20
Config Update |  |  | 10 |  | 10
Unit Test |  | 0 | 20 |  | 40
Operation Acceptance Test
Prepare OAT Cases (including Resilience (HA) Test) |  | 2 | 2 | [5 empty] | 26) Operation Acceptance Test Cases
Conduct OAT Testing |  | 4 | 4 | [5 empty] | 26) Operation Acceptance Test Report | Scope of OAT - Resilience (HA) - Cluster Failover (Stop/Re-start) - 8 Main Cases Included
Implementation
Prepare Implementation Plan |  | 2 | 3 |  | 4 |  |  |  | 27) Implementation Plan (D) (T) 28) Project QA Checklist (D)(T) | Prepare, review 2 rounds, and final work through.
Production Setup Implementation |  | 6 | 6 | [5 empty] | 29) Release Request Form (D)(T) | Depend on actual channel release phases, 2 MD for each phase and assume 3 phases are required
Documentation
Review and Confirm Operational Manual |  | 3 | 2.5 | [5 empty] | 25) Operational Manual (D) | Revision 2MD, 2 Rounds Review
Post Implementation
Maintenance Transition | 5 | 3 | 5 | [5 empty] | 30) Knowledge Transfer Review Checklist (D)(T)
Post Implementation Support |  | 20 | 15
Discount
| 55 | 342.5 | 312 | 0 | 265 | 0 | 0 | 0
Assumption: | 440 | 2740 | 2496 | 0 | 2120 | 0 | 0 | 0
| 530 |  | 510 | 420 | 300 | 510 | 420 | 300
| 233200 | 0 | 1272960 | 0 | 636000 | 0 | 0 | 0 | 2142160
0
2142160