## Sheet1
No. | Type | Questions | Answer
1 | Configuration | Where to define the list of POS clients for Polling, in DB or in configruation file (xml, plain text, etc)? | [Steven]: The POS polling list will be configured in the working DB of the ESB
2 | System | How to control different Polling threads to poll the same POS client at the same time? | [Steven]: The threads in the pool will open connection to POS client on the basis the round robin rule
3 | Requirement | What Sales/EOD tables should be treated as group, e.g. ORDER, TRANS and ORDER_PAY? And how to link those records together, i.e. Key fields to join the tables.
4 | Requirement | What is the commitement cycle done by the POS client? Did the sales data committed by group? If not, Some order might have integrity issues, e.g. ORDER w/o TRANS or w/o ORDER_PAY, etc. | [Steven]: After the reord is successfully polled into working DB and consolidated to invoke sales data update service, the application will change the indicator in POS client DB
5 | Requirement | How to handle the missing records in the group of sales/EOD data? Ignore or generate alert message? | [Steven]: false records will retained in exceptional data table in working DB, which would be exported and attached in the alert email. Ext. Question: [Steven] What could be done by Service Bus if false data occurs
6 | Requirement | Any OLD data might violate the checking rules, e.g. total TRANS amount <> amount in ORDER? For example, cancelled/void ORDER might not pass the above checking. | [Steven]: These data will also be put into exceptional data table Ext. Question: [Steven] Service bus does not suppose to handle any business logic. Which system will take over the check sum logic in the future?
7 | System | Sales/EOD ESB interfaces should transfer multiple records in a call for performance issue. | [Steven]: The handling outbound data from ESB to EDW should be handle one order data in each transaction.
8 | Requirement | How to handle duplicate sales data being re-uploaded to ESB? Overwrite the existing or generate alert? For example, ESB interface program errors and resume the job might cause the re-uploading of the same of sales/EOD data? | [Steven]: The uuid fields in various table will be considered as the key to check whether the data is duplicated uploaded. Ext. Question: [Steven] Does the "orders.uuid" could be consider the unique key for an order item? Or "orders.order_no"? Ext. Question: [Steven] Can order_no be considered as the relational foreign key amoungst orders, orders_extra, orders_pay. Any tables are missing?
9 | Requirement | How to reconcile the branch EOD data against the EDW EOD data for any mssing records? For example, checking total count and total amount between these two systems. | [Steven]: Same query as #6
10 | System | If data in POS Polling server does not reconcile with EDW, how ESB system to resolve this issue? | [Steven]: Suggest that the data is blocked by ESB because of data discrepancy or failure invoking the service to EDW. So suggest an exceptional data handline process toward EDW to be introduced
11 | System | How to ensure the data sent to EDW is the same as the data sent to POS Polling Servers? Existing application still use the Polling server data for batch processing or analysis. | [Steven]: This question sounds like how to ensure the passenger getting on the bus and off the bus is the same passenger.
12 | Requirement | If a sales/EOD record update encounter errors, how we can handle this error? | [Steven]: Suggest that the EOD processing against the records in history tables also have a flag indicating it's processed or not. The re-run of the EOD processing should only handle those pending for process
13 | System | How to simulate/replicate the features of the existing POS Polling control tables, i.e. - synchronizaiton direction - pricing / master data can be upload or download - synchronize period - pricing data will be synchronize on particular instead of always syncrhonized, e.g. master data synchronize between 03:00 to 06:00. - partial / full overwrite flag - control whether to overwrite the target tables in either POS Polling server or POS client
14 | System | if the control tables/configuration had been changed, how to make effect this changes? Need to restart the ESB to reload the new configuration? | [Steven] if maintained by DB that the configuration could take effect immediately. This control table's owner is IT so it'd better not change frequently.
15 | Requirement | how to determine the POS client EOD completed? Which tables to be checked? All HIST_ tables should be updated before the EOD flag being marked completed, correct?
16 | Requirement | How to acknowledge the EDW system, the EOD data is ready for processing? EDW system periodically lookup a branch table or acknowledge message send to EDW for alert? | [Steven] Approach 1. POS Client invokes a service telling ESB to submit the EOD processing Job for him [Steven] Approach 2. POS Client can only update a record in local DB. ESB should have a process keep scanning the POS client local indicator. Once it is changed to EOD status, submit a job for that client.
17 | Requirement | Is it true that system will stop polling client after the EOD data is completely transfer to EDW? If yes, when the polling restart to capture the POS client data. If no, how to handle the 7x24 POS client, e.g. Macau's starbucks. | [Steven] the time frame in control table will represent whether the client is under polling process. E.g. if current time is not within the client's time frame, the process for this client will skip.
18 | Requirement | Currently, latest Pricing and Master data will be retrieved/generated when polling. How and when Pricing or Master data will be generated into the stagging tables? Is it a schedule to generate the Pricing / Master data? | [Steven] Approach 1. Schedule job to trigger udsp_gen_pricing. pull full table data to working DB, and publish to remote POS client. Monitor publish status. [Steven] Approach 2. Use DB adapter to pull Up-to-date data to working DB. Server periodically publish changes to remote POS. Monitor publish status. Note: require further study in udsp_gen_pricing, seeing it's full tables override or delta merge process to determine using 1 or 2
19 | System | How to prevent ESB system to concurrent access the same POS clients for pricing or master data updating? | [Steven] Same answer as #2
20 | Requirement | For SQL DB, how to update POS client's local DB, incremental update or fully overwrite. That's whether we delete the whole tables content in local DB and insert the Pending records? OR, delete whose records in local DB which to be synchronized? | [Steven]: depend on whether the override indicator is ON for the data pushing
21 | Requirement | Is there any relationship between the Pricing or Master data which must be fulfilled? For example, we should update the ITEM successfully before we update the PRICING. If ITEM fails, we should skip the PRICING records.
22 | Requirement | Currently, too much alert email being generated for the unattend error, e.g. repeat email alert for the network connectivity issue. What is the expected handling for alert message generation to mininize these repeated message? | [Steven]: Exception severity will be introduced.
23 | Requirement | Email alert will be generated for each records or generated for each job/process? | [Steven]: the email alert sending will depend on the severity. Maybe detail exception list is sent out hourly as a hourly report
24 | System | How user/operator to review the detail of error? Error detail can be found in email or operator need to collect the log manually from ESB log? | [Steven]: Answered in #23
25 | System | System will automatially retry/re-run the job/process? Or, system will stop retry for some critical conditions, e.g. network connection error or DB error? | [Steven] System only retries on connection error caused by network or DB. If encounter data error, the exceptional data will be written into error table and skipped.
26 | System | If job/process abort, how operator to resume the process. Start one-by-one or start them all at once? | [Steven] A job control UI should be provided for mannual triggering. We could use an indicator to indicator the job for target POS client is paused or resume running. Aborting the job is not suggested
27 | Requirement | How system count the retry of job processing? For example, any error occurred will be counted or only particular error will be counted. | [Steven] Job is trigger in a configured time interval, e.g. 15mins. The failure of last run should not block the next run within a same job.
28 | Requirement | What is the polling logic difference of the SP in different DB IT51, IT52 and IT53?
29 | Requirement | What is the report content for operation report generated by system hourly?
30 | Requirement | What is the report content for the ESB exception report? What is the selection criteria, i.e. what exception wanted to be printed? What is the time to generate this exception report?