## Maxims POS Polling ESB Implemen
# | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete | Notes
1 | Maxim's ESB Development | 31 days | Mon 2/6/17 | Mon 3/20/17 |  |  | 1%
2 | Data Model Definition | 1 day | Mon 2/6/17 | Mon 2/6/17 |  | Steven | 100%
3 | Work Flow Pseudo Coding | 2 days | Tue 2/7/17 | Wed 2/8/17 |  | Steven | 20%
4 | Story Telling on Overall Project Background | 1 day | Fri 2/10/17 | Fri 2/10/17 | 2 | Steven,Edward,Gavin,Johnson,Joy,Lotic | 100% | Present all requirements to all developers, develop write back logic and technical spec
5 | Common Model | 7 days | Thu 2/9/17 | Fri 2/17/17 |  |  | 0%
6 | FTP Server (for FTP based file download) | 1 day | Thu 2/9/17 | Thu 2/9/17 |  | Lotic | 0%
7 | File Copy Service (Network Drive File Copy) | 1 day | Fri 2/10/17 | Fri 2/10/17 | 6 | Lotic | 0%
8 | Job Control Services | 2 days | Mon 2/13/17 | Tue 2/14/17 |  | Gavin | 0%
9 | JDBC Utility | 5 days | Mon 2/13/17 | Fri 2/17/17 |  | Steven | 0%
10 | Export DBF / CSV / Text | 3 days | Mon 2/13/17 | Wed 2/15/17 |  | Joy | 0%
11 | ESB Core Data Polling | 11 days | Mon 2/13/17 | Mon 2/27/17 |  |  | 0%
12 | POS to Staging - Real Time | 5 days | Mon 2/13/17 | Fri 2/17/17 | 7 | Johnson | 0% | Lotic Support
13 | POS to Staging - End of Day | 3 days | Mon 2/20/17 | Wed 2/22/17 | 12 | Johnson | 0% | Lotic Support
14 | Staging to EDW - Real Time | 5 days | Wed 2/15/17 | Tue 2/21/17 | 8 | Gavin | 0% | STG -> Web Services API -> EDW, Steven Support
15 | Staging to EDW - End of Day | 4 days | Wed 2/22/17 | Mon 2/27/17 | 14 | Gavin | 0%
16 | Master/Pricing Data (Staging to POS) | 5 days | Mon 2/13/17 | Fri 2/17/17 |  | Joy | 0% | Steven support
17 | DB Adaptor Monitor | 3 days | Thu 2/16/17 | Mon 2/20/17 | 10 | Lotic | 0% | Steven support
18 | Copy Data from (IT12 or IT50) to Staging | 3 days | Mon 2/20/17 | Wed 2/22/17 | 16 | Joy | 0% | Steven support
19 | Systems Configuration User Interface / Others | 20 days | Tue 2/21/17 | Mon 3/20/17 |  |  | 0%
20 | User Maintenance (Completed) | 0 days | Tue 2/21/17 | Tue 2/21/17 | 17 |  | 100%
21 | System Parameter Configuration | 4 days | Tue 2/21/17 | Fri 2/24/17 | 17 | Joy | 2%
22 | Branch Info Maintenance | 3 days | Tue 2/28/17 | Thu 3/2/17 | 15 | Gavin | 0%
23 | Branch Scheme Maintenance | 15 days | Thu 2/23/17 | Wed 3/15/17 | 18 | Johnson | 0%
24 | Scheduler Jobs Maintenance | 5 days | Mon 2/27/17 | Fri 3/3/17 | 21 | Joy | 0%
25 | Alert Email | 4 days | Mon 3/6/17 | Thu 3/9/17 | 24 | Joy | 0%
26 | Export Daily Report | 4 days | Thu 2/23/17 | Tue 2/28/17 | 13 | Lotic | 0%
27 | Job Logs View | 6 days | Fri 3/3/17 | Fri 3/10/17 | 22 | Gavin | 0%
28 | Systems Dashboard | 3 days | Wed 3/1/17 | Fri 3/3/17 | 26 | Lotic | 0%
29 | Backup and Housekeeping | 6 days | Mon 3/13/17 | Mon 3/20/17 | 27 | Gavin | 0%